## USER GUIDE
REAL ESTATE FEASIBILITY ENGINE — USER GUIDE
A complete, step-by-step manual for anyone using the feasibility workbook (Feasibility_Engine_FINAL.xlsx). Read Parts 1–3 once; then use Part 4 while filling inputs and Parts 7–8 whenever you need a quick answer.
PART 1. BEFORE YOU START – 7 GOLDEN RULES
Rule | What it means | Why | Where
1. Open in Microsoft Excel | Use desktop Microsoft Excel. Google Sheets / LibreOffice open the file but the STRESS tables stay blank there. | The stress tables are Excel 'Data Tables', an Excel-only feature. | Whole file
2. Work on a copy | Before every new project: File → Save As → give it the project name (e.g. 'Feasibility_Land1250_v1.xlsx'). Keep the original as a clean template. | You can always go back to a clean, tested template. | File menu
3. Type only in blue-on-yellow cells | Blue text on a light-yellow background = input. Black text = formula. Green text = link from another sheet. | Typing over a black or green cell breaks the calculation chain silently. | Mainly the INPUTS sheet; levers on STRESS
4. Use the dropdowns | Many inputs have a dropdown arrow (deal type, curves, CLP plan, Yes/No …). Always pick from the list; do not type free text. | The model matches exact words – a typo = an ERROR flag. | INPUTS
5. Quarters are numbers | Every timing input is a quarter NUMBER counted from the project start date. Type 3 and the cell shows Q3. | Q1 = the quarter ending on the 'Project start' date. | INPUTS Sections 5, 6, 7
6. Never insert / delete rows or columns | To remove something, clear its contents or set it to 'No'. Spare rows already exist for additions. | All sheets are linked by position; inserted rows break links. | All sheets
7. Status must be green | Top of INPUTS (and the DASHBOARD header) must read '✔ ALL CHECKS PASSED' before you use or share any number. | 75+ automatic checks protect you from wrong inputs. | INPUTS Section 0, DASHBOARD row 4
PART 2. MAP OF THE WORKBOOK – WHAT EACH SHEET DOES
Sheet | Purpose | Do I type here? | Use it for
README | Short overview, colour code and build roadmap. | No | First orientation
DASHBOARD | One-page summary: 12 KPI tiles (green = beats benchmark, amber = review), 4 auto-written takeaways, 6 charts incl. Gantt. | No | Management review, screenshots, printing
STRESS | What-if tables: Best/Base/Worst side by side, price / cost / sales-speed / delay sensitivities, heat maps, headroom. | Only the 5 levers – and keep them at neutral | Risk discussion
INPUTS | THE ONLY PLACE YOU FILL DATA: project, land, scenarios, zones, products, timing links, 21 cost heads, calculators, payment plans, tax, benchmarks, checks. | YES | Setting up every new project
TIMELINE | 40 quarter columns (10 years) with dates, financial year, phases, Gantt, and on/off flags for sales, construction and cost windows. | No | Checking when things happen
CURVES | Turns curve names (Even, S-curve …) into quarterly % for sales, construction and every cost head – always totalling 100%. | No | Checking how spends are spread
COLLECTIONS | Bookings → payment-plan milestones → actual cash received, per product; milestone schedule in plain English; JV split. | No | Checking customer cash inflows
CASHFLOW | Outflows by cost head, landowner payments, project & developer cash flow, IRR, NPV, peak investment, payback, yearly (FY) summary. | No | Funding and returns analysis
OUTPUT | Investment report: A Revenue, B Cost, C P&L, D JV split, E 18 key metrics with benchmark status. | No | Formal reporting (same layout as earlier feasibility formats)
LISTS | Dropdown lists, unit conversions (incl. bigha factor) and curve definitions. | Rarely (only conversion factors) | Changing the bigha size for another state
Flow of calculation: INPUTS → TIMELINE (when) → CURVES (how much per quarter) → COLLECTIONS (cash in) → CASHFLOW (cash out, returns) → OUTPUT / DASHBOARD / STRESS.
PART 3. QUICK START – A NEW PROJECT IN 12 STEPS
Step | Action | Tip | Where
1 | Save a copy of the template with the project name. | Never work in the master file. | File → Save As
2 | Fill project details: name, location, project type, start date, deal type, taxable entity, scenario = Base Case. | Start date must be a quarter end: 31-Mar, 30-Jun, 30-Sep, 31-Dec. | INPUTS Section 1
3 | Fill land: area (sq yd), market rate (₹/sq yd), DLC rate (₹/sq m); JV share or outright purchase rate. | Conversions to sq ft, acres, bigha are automatic. | INPUTS Section 2
4 | Set development-zone shares of land. | Total must not exceed 100%. | INPUTS Section 4
5 | Enter products: one row each – name, zone, category, area, sales rate, construction rate, sales period, curves, payment plan; set 'Include? (your choice)' = Yes in column X. | Column E 'Active?' fills itself from your choice + project type. | INPUTS Section 5
6 | Decide launch & construction start for each product: fixed quarter or linked to another product. | Put the lead product (the one launched first) in the first row. | INPUTS Section 5B
7 | Review the 21 cost heads: rates, 'Applicable?' Yes/No, phasing curve, start/end quarters. | Most heads already 'Follow' sales / construction – they adapt automatically. | INPUTS Section 6
8 | Fill calculators: BAR / premium FAR, AIF (if used), initial investment payout schedule. | Switch AIF on only if land is AIF-funded. | INPUTS Section 7
9 | Check / edit payment plans (CLPs) and the catch-up lag; assign a plan to each product. | Each plan must total exactly 100%. | INPUTS Section 8
10 | Confirm tax rates, cost of equity and KPI benchmarks with Finance. | Defaults are placeholders, not verified rates. | INPUTS Section 9
11 | Scroll to the top: status must read '✔ ALL CHECKS PASSED'. If not, see Section 10 of INPUTS and Part 8 of this guide. | Fix errors from the top of the list downwards. | INPUTS Sections 0 & 10
12 | Read results on DASHBOARD and OUTPUT; run risk view on STRESS (press F9 if tables look old). | Never share numbers unless the status reads ✔ ALL CHECKS PASSED. | DASHBOARD, OUTPUT, STRESS
PART 4. INPUTS SHEET – FIELD-BY-FIELD INSTRUCTIONS
Sections below follow the INPUTS sheet from top to bottom. 'Example' values are from the sample project and are only illustrations.
Field | What to enter / what it does | Example & tips | Location
SECTION 0 – Model health | Shows the status, number of errors, and a mini snapshot (GDV, total cost, EBITDA margin, PAT). Nothing to type. | ✔ = OK. ✖ = errors to fix. ⚠ = checks passed but STRESS levers are not at neutral (results are stressed). | Top of INPUTS
SECTION 1 – Project & timeline
Project name / Location | Free text; appears on the DASHBOARD and OUTPUT. | Project Aurora, Sample City | INPUTS Section 1
Project type | Villa / Plotted / Apartments / Mixed Development. Controls which products are calculated: only products whose development zone matches the type are active. Mixed = all zones. | Pick Apartments and every villa/plot row becomes 'Excluded' automatically. | INPUTS Section 1
Project start (quarter-end date) = Q1 | The quarter in which the project starts; every quarter number in the model counts from here. | 30-Jun-2027 → Q1 = Apr–Jun 2027. | INPUTS Section 1
Deal type | JV = landowner gets a revenue share; Outright = land bought for cash. | Changes land cost, stamp duty, brokerage base, initial investment and landowner payments. | INPUTS Section 1
Taxable entity | Company or LLP – picks the tax rate in Section 9. |  | INPUTS Section 1
Active scenario | Best / Base / Worst – adjusts sales speed, price, construction cost and delay (defined in Section 3). | Use Base Case for the main feasibility. | INPUTS Section 1
Model horizon (quarters) | Engine length = 40 quarters (10 years). Do not change. | If the project needs more than 10 years, contact the model owner. | INPUTS Section 1
Crore divisor | Unit constant 1,00,00,000. Do not change. |  | INPUTS Section 1
Lifecycle override (optional) | Years used for ROCE and CAGR. Leave blank to use the derived project span. | Type 4 to reproduce an older model that assumed 4 years. | INPUTS Section 1
Derived rows | Horizon end date, project last active quarter/date, project span – automatic. | Use these to confirm the project length looks right. | INPUTS Section 1
SECTION 2 – Land
Land area (sq yd) | Total land area. Sq ft, sq m, acres and bigha are calculated. | Bigha factor (3,025 sq yd, Rajasthan) can be edited on LISTS for other states. | INPUTS Section 2
Current market rate (₹/sq yd) | Today's market land rate. | Used for land value, brokerage (JV) and the landowner price check. | INPUTS Section 2
DLC rate (₹/sq m) | Government guideline (circle) rate, entered per sq m; converted to per sq yd automatically. | Used for stamp duty. | INPUTS Section 2
JV ratio – Landowner | Landowner's share of total revenue (JV only). | 32% → developer gets 68%. | INPUTS Section 2
Stamp duty – JV (% of DLC value) | Rate applied on DLC value × land area. | Verify the current state rate. | INPUTS Section 2
Land rate for purchase / Stamp duty – Outright | Outright only: price per sq yd and stamp duty % (charged on the higher of DLC value and purchase price). |  | INPUTS Section 2
Land payment curve / start / end | Outright only: how the land price is paid (Upfront or spread). | Upfront in Q1, or Even over Q1–Q4. | INPUTS Section 2
Land price check | Automatic: market vs price effectively offered to the landowner, per bigha and per sq yd, with % uplift. | Positive uplift = landowner earns more than selling today. | INPUTS Section 2
SECTION 3 – Scenarios | Each row = one scenario: sales period multiplier (1.5 = sales take 50% longer), sales price change %, construction cost change %, delay in quarters. Edit the numbers if your company uses different stress levels; keep the three names. | Worst Case sample: 1.5x slower, −7.5% price, +7.5% cost, 2-quarter delay. | INPUTS Section 3
SECTION 4 – Development zones | Share of land for Villa, Apartment, Plotted and Other/Clubhouse development. Land area per zone is calculated; saleable area and revenue per zone come from the products. Column 'In this project type?' shows which zones are used. | Total share must be ≤ 100%. | INPUTS Section 4
SECTION 5 – Product mix | One row per product (10 rows available). Columns: |  | INPUTS Section 5
B – Product name | Unique name (used for timing links). | Villas; Apartments – Towers A & B | INPUTS Section 5
C – Development zone | Villa / Apartment / Plotted Development / Other. Decides if the product is active for the chosen project type, and plotted marketing rate. |  | INPUTS Section 5
D – Category | Villa, Apartment, Studio, Plot, Commercial, Institutional, EWS/LIG. Decides which construction cost head the product's cost goes to. | Studios → 'Studio Construction cost with furnishing'. | INPUTS Section 5
E – Active? (automatic) | Yes only if column X = Yes AND the zone matches the project type. Do not type here. |  | INPUTS Section 5
F, G, H – Area, sales rate, construction rate | Saleable area (sq ft), base sales rate (₹/sq ft), construction cost (₹/sq ft of saleable area). | 600,000 sq ft @ ₹7,500 with ₹2,900 construction. | INPUTS Section 5
I – Launch quarter (if Fixed) | Quarter number when sales start – used when Section 5B says 'Fixed quarter' (and as fallback). | 3 = Q3 | INPUTS Section 5
J, K – Sales period, sales curve | How many quarters to sell out, and the shape (Even, Front-loaded, Back-loaded, S-curve). | 8 quarters, Front-loaded = faster early sales. | INPUTS Section 5
L – CLP / payment plan | Pick the payment plan from the dropdown (plans are defined in Section 8). | CLP – Villa | INPUTS Section 5
M, N, O – Construction start (if Fixed), duration, curve | Construction start quarter, number of quarters, and shape (S-curve is typical). | Start Q4, 12 quarters, S-curve. | INPUTS Section 5
P to V – automatic | Final launch/sales-end/construction quarters after scenario & links, revenue, construction cost, launch date. | Check these look sensible. | INPUTS Section 5
W – Row check | OK / Off / Excluded / ERROR. | Excluded = switched off by project type. | INPUTS Section 5
X – Include? (your choice) | Yes to use the product, No to keep it saved but switched off. | To add a product: fill a spare row and set X = Yes. | INPUTS Section 5
SECTION 5B – Product timing | For each product choose HOW its launch and construction start are decided: |  | INPUTS Section 5B
Launch timing | Fixed quarter (uses column I) ¦ Linked to another product ¦ After own construction start. | Apartments: Linked to Villas – Launch, offset 1. | INPUTS Section 5B
Construction timing | Fixed quarter (uses column M) ¦ After own launch ¦ Linked to another product. | Villas: After own launch, offset 1. | INPUTS Section 5B
Linked product / event | Product must be listed ABOVE in the table. Events: Launch, Sales end, Construction start, Construction 50%, Construction end. | Retail: 4 quarters after Apartments – Launch. | INPUTS Section 5B
Offset (quarters) | 0 = same quarter as the event, 1 = next quarter, −1 = one quarter before. |  | INPUTS Section 5B
Plain-English result | Automatic sentence describing the final quarters – read it to confirm your intention. | 'Launch Q8 (4 qtr(s) after Apartments – launch)' | INPUTS Section 5B
Fallback | If the linked product is not active (e.g. excluded by project type), the fixed quarter in Section 5 is used and the sentence says 'fixed fallback'. | Keep a sensible fixed quarter in columns I and M for every product. | INPUTS Section 5B
SECTION 6 – Cost heads | 21 standard heads + 3 spare rows. For each: Rate / Input 1, Input 2 (if any), Applicable? (Yes/No), phasing curve, start & end quarter. Amount, ₹/sq ft and % of GDV are automatic. | Set 'Applicable?' = No to switch a head off instead of deleting it. | INPUTS Section 6
Land Cost / Stamp Duty / Brokerage | Linked to Section 2. Brokerage % is entered here (Input 1). | JV land cost is paid as the landowner's share of each collection. | INPUTS Section 6
7 construction heads | Villa, APT, Studio, Plotted, Institutional, Commercial, EWS/LIG – automatic sums of products by category; follow each product's construction curve. | Change rates in the product table, not here. | INPUTS Section 6
Corporate Overheads | % × total revenue (Input 1). | 4% – spread over project life. | INPUTS Section 6
Marketing & Sales | Input 1 % × built-up revenue + Input 2 % × plotted revenue. | 7% and 5%; follows sales. | INPUTS Section 6
Legal & Compliance | ₹/sq ft × total saleable area. | ₹75/sq ft, front-loaded Q1–Q8. | INPUTS Section 6
EWS / LIG | Loss ₹/sq ft (Input 1) × EWS share of SA (Input 2) × total SA. | ₹400 × 5%. | INPUTS Section 6
Contingency | % (Input 1) × base chosen in Input 2 (construction cost or all costs excl. land). | 0% by default. | INPUTS Section 6
External Development & Landscaping | Input 1 applied per basis in Input 2 (₹/sq ft, % of construction, or lump sum). |  | INPUTS Section 6
Hotel Brand Key fee | Fee per key (₹) × number of keys (Input 2). | ₹50,000 × keys; 0 keys = not applicable. | INPUTS Section 6
Furnishing Cost for Studios | ₹/sq ft × studio area. Keep 'No' if the studio construction rate already includes furnishing. | Avoid double counting. | INPUTS Section 6
GST on unsold inventory | Commercial + plot revenue × unsold % × GST % × developer share. Paid at project end. | Off by default. | INPUTS Section 6
AIF Cost / BAR | Linked to the calculators in Section 7; switch with 'Applicable?'. |  | INPUTS Section 6
Spare rows | Name, basis (dropdown), rate, Applicable, curve, start/end. | Use for any extra cost (e.g. clubhouse fit-out). | INPUTS Section 6
Phasing curve | Upfront / Even / Front-loaded / Back-loaded / S-curve need start & end quarters. 'Follow Construction / Sales / Collections / Project Life' and 'At Project End' adjust automatically (start/end greyed out). | Prefer 'Follow …' curves – they adapt when timelines change. | INPUTS Section 6
SECTION 7 – Calculators
7A BAR / Premium FAR | Authority (RIICO/JDA), land use, free FAR, loading factor, reserved price, GST switch and the % table. Extra BAR = planned area − free area; cost = extra × reserved price × %. | A blank % in the table = combination not allowed (ERROR). | INPUTS Section 7
7B AIF | Principal = land + stamp duty + brokerage (auto), interest rate, tenure, compounding. | Activate via 'Applicable?' on the AIF cost head. | INPUTS Section 7
7C Initial investment – JV | Advance to landowner (% of market land value), DD and DA instalments (token = balance), share of legal and BAR paid upfront, pre-DA development & pre-launch marketing, and the payout QUARTER of each item. | These are paid early in the cash flow; the cost heads pay only the balance – nothing is counted twice. | INPUTS Section 7
7D Initial investment – Outright | Land + stamp duty + brokerage + % of built-up construction + % of legal. | Used for ROCE / CAGR in Outright deals. | INPUTS Section 7
SECTION 8 – Payment plans (CLP) | 6 plan slots × 30 milestones. Catch-up lag (top of section): quarters after booking in which late buyers pay milestones already reached (1 = with ATS). |  | INPUTS Section 8
Plan name | Unique name; appears in the product dropdown (column L). | CLP – 17-Floor Tower | INPUTS Section 8
Milestone / trigger type / trigger value / % of sale | Booking + quarters (value 0–12 = quarters after booking) or Construction % complete (value 0%–100% of that product's construction). | ATS: Booking + 1. Slab floor 5: Construction 26.5%. | INPUTS Section 8
Plan total & status | Must total exactly 100% → OK. Empty slot → Unused. |  | INPUTS Section 8
Adding milestones | Type them in the next empty rows of the plan; re-balance %s to 100%. No other change needed anywhere. | 8-floor → 17-floor: add slab rows, adjust %s. | INPUTS Section 8
Using a blank slot | Type a new plan name + milestones, reach 100%, then assign it to a product in Section 5 column L. |  | INPUTS Section 8
Removing a plan | First re-assign any product using it, then clear the name and milestone cells (do not delete rows). |  | INPUTS Section 8
SECTION 9 – Tax, returns & benchmarks | Tax rates for Company / LLP (applied automatically), cost of equity (discount rate for NPV), and KPI benchmarks used for the green/amber status. | Get these confirmed by Finance for every real deal. | INPUTS Section 9
SECTION 10 – Model checks | List of every check with OK / ERROR and what to fix. The count feeds the status at the top. | Always fix the FIRST error first – later ones are often caused by it. | INPUTS Section 10
PART 5. READING THE RESULTS
Where | What you see | How to read it | Watch out for
DASHBOARD – KPI tiles | GDV, total cost, EBITDA, PAT, developer & project IRR, NPV, equity multiple, peak investment, payback, ROCE, CAGR. | Green tile = beats the benchmark in INPUTS Section 9; amber = review. | Project IRR is before the landowner share – judge the deal on DEVELOPER IRR.
DASHBOARD – takeaways | Four sentences written by the model. | Copy into notes / emails; they update automatically.
DASHBOARD – charts | Developer cash flow & funding curve, cost breakdown, revenue by type, cash by financial year, cumulative cash in vs out, timeline Gantt. | Lowest point of the cumulative line = peak investment.
OUTPUT | A Revenue statement, B Cost statement, C P&L (EBITDA, tax, PAT, margins), D JV split, E 18 key metrics with benchmark and formula notes. | Formal format for approval committees. | Tax is applied only on positive EBITDA.
CASHFLOW | Quarter-by-quarter inflows, outflows by head, landowner payments (advance recovery), net project & developer cash, IRR/NPV block, FY summary. | Section E gives peak investment quarter/date, break-even and payback. | Post-tax IRR is indicative only.
COLLECTIONS | Milestone schedule (which quarter each milestone falls due), bookings, booking-linked and construction-linked collections, receivables, JV split. | Receivables = sold but not yet paid. | 'NOT REACHED in model' = construction never reaches a trigger – check durations.
TIMELINE / CURVES | When things happen (Gantt, phases, windows) and how spends are spread (% per quarter). | Use to explain timing questions.
PART 6. STRESS TESTING – HOW TO USE THE STRESS SHEET
Step | Action | Tip | Where
1 | Keep all 5 levers at neutral: price 0%, cost 0%, sales period 1.00x, delay 0, scenario override 0 (and output selector 1). | If a lever is left on, the status shows '⚠ STRESS levers are active'. | STRESS Section A
2 | Press F9 to refresh the tables after changing inputs. | If Excel becomes slow: Formulas → Calculation Options → 'Automatic except for Data Tables', then use F9. | Excel ribbon
3 | Read B – Scenario comparison for Best / Base / Worst side by side. |  | STRESS Section B
4 | Read C1–C4 one-way sensitivities (price, cost, sales speed, delay). | Speed and delay usually hurt IRR more than price – cash timing matters. | STRESS Section C
5 | Read D1–D3 heat maps (red = worse, green = better). | Find the combination where IRR falls below the hurdle. | STRESS Section D
6 | Read E – headroom: price fall / cost overrun that wipes out EBITDA. | Quote these in approval notes: 'prices can fall X% before EBITDA = 0'. | STRESS Section E
Do not | Do not type inside the tables – they are Data Tables and will reject edits.
PART 7. COMMON TASKS – HOW DO I …?
Task | Steps | Result | Where
Change project duration | Change sales period (J) and/or construction duration (N) of the products. Nothing else. | Timeline, curves, CLP dates, collections, costs and returns all re-flow. | INPUTS Section 5
Add a new product | Fill a spare product row (name, zone, category, area, rates, periods, curves, plan), set X = Yes, set its timing in 5B. | It appears in every sheet and chart. | INPUTS 5 & 5B
Remove a product temporarily | Set X = No. | Row shows 'Off'; data kept. | INPUTS 5, column X
Run a Villa-only / Apartment-only feasibility | Change Project type in Section 1. | Other zones' products show 'Excluded'; links fall back to fixed quarters. | INPUTS Section 1
Switch JV ↔ Outright | Change Deal type; for Outright fill purchase rate, stamp duty % and land payment curve. | Land cost, landowner payments, initial investment and returns update. | INPUTS 1 & 2
Add floors / milestones to a CLP | Fill extra rows in the plan, re-balance to 100%. | No other change needed. | INPUTS Section 8
Create a new payment plan | Use a blank plan slot: name + milestones = 100%, then pick it in column L for the product. |  | INPUTS 8 & 5
Delay a launch | Change the fixed launch quarter (I) of the lead product – linked products move with it. Or use the scenario delay. |  | INPUTS 5 / 5B / 3
Change how a cost is spread | Change its phasing curve / start / end quarter. | CURVES re-spreads it to 100%. | INPUTS Section 6
Switch off a cost head | Set Applicable? = No. | Amount becomes 0; row greyed. | INPUTS Section 6
Add a cost not in the list | Use a spare cost row: name, basis, rate, Applicable = Yes, curve. |  | INPUTS Section 6
See the Worst Case | Select Worst Case in Active scenario – or read it on STRESS Section B without changing inputs. |  | INPUTS 1 / STRESS
Change benchmarks | Edit KPI benchmarks. | Tile colours update. | INPUTS Section 9
Change bigha size (other state) | Edit the bigha factor on LISTS (units per sq yd = 1 ÷ sq yd per bigha). |  | LISTS conversion table
Print / PDF the dashboard | Select DASHBOARD → File → Print (landscape, fit to width is preset) or Save as PDF. |  | DASHBOARD
PART 8. TROUBLESHOOTING – ERROR MESSAGES AND FIXES
Message / symptom | Likely cause | Fix | Where
✖ n ERROR(S) – see Section 10 | One or more checks failed. | Go to INPUTS Section 10, fix the first ERROR, re-check. | INPUTS 10
⚠ CHECKS PASSED – but STRESS levers are active | A STRESS lever is not at neutral. | Reset levers: 0%, 0%, 1.00x, 0, 0, 1. | STRESS A
Project start is not a quarter-end date | Date like 15-Jul typed. | Enter 31-Mar, 30-Jun, 30-Sep or 31-Dec. | INPUTS 1
Product row check = ERROR | Blank required field, invalid plan, or timing beyond Q40. | Fill all columns; pick a valid plan; shorten timing. | INPUTS 5
Product row = Excluded | Its zone does not match the Project type. | Expected – change Project type to Mixed if you want it. | INPUTS 1 / 5
Product timing links valid = ERROR | Linked product is below this row, misspelt, or missing a fixed fallback. | Re-order products (lead product first) or choose Fixed quarter. | INPUTS 5B
Product names unique = ERROR | Two products share a name. | Rename one. | INPUTS 5
Payment plan = ERROR | Plan total ≠ 100%, incomplete milestone row, booking lag > 12, or duplicate plan name. | Correct the %s / row / name. | INPUTS 8
Cost row = ERROR | Missing rate, wrong curve, start > end, or quarter beyond 40. | Correct that row. | INPUTS 6
Zone shares > 100% | Zone shares add above 100%. | Reduce shares. | INPUTS 4
BAR calculator = ERROR | Authority / land-use combination has no % (e.g. JDA Industrial). | Choose a valid combination or fill the %. | INPUTS 7A
Initial investment = ERROR | DD + DA instalments exceed the total advance, or payout quarter invalid. | Reduce instalments; use quarters 1–40. | INPUTS 7C
Project fits inside model horizon = ERROR | Sales/construction run past Q40. | Shorten periods or delays. | INPUTS 5 / 3
Milestone 'NOT REACHED in model' | Construction never reaches the trigger %. | Check construction duration / product timing. | COLLECTIONS A
Developer IRR shows 'n/a' | Cash flow never turns positive (or no sign change). | Check costs vs revenue; the deal may be loss-making. | CASHFLOW E
STRESS tables blank | File opened outside Excel, or tables not refreshed. | Open in Microsoft Excel and press F9. | STRESS
Excel slow | Data Tables recalculate the whole model many times. | Calculation Options → Automatic except for Data Tables; F9 when needed. | Excel ribbon
A number looks wrong but no error | An input typo (e.g. 75000 instead of 7500). | Check the ₹/sq ft and % of GDV columns in Section 6 and revenue in Section 5 for outliers. | INPUTS 5 & 6
PART 9. GLOSSARY – KEY TERMS IN SIMPLE WORDS
Term | Meaning | Example / formula
GDV | Gross Development Value – total sales value of the project. | Area × rate, all products.
EBITDA | Profit before tax (revenue − all project costs). | GDV − total cost.
PAT | Profit after tax. | EBITDA − tax.
IRR | Annual return earned on the money invested, considering timing. | (1 + quarterly IRR)^4 − 1.
Developer IRR vs Project IRR | Developer IRR is after paying the landowner; Project IRR is before. | Judge the deal on developer IRR.
NPV | Today's value of all future cash flows, discounted at the cost of equity. | Positive NPV = value created.
Peak investment | Maximum money the developer must put in before cash comes back. | Lowest point of cumulative developer cash.
Payback / break-even | Payback = quarter when cumulative cash returns to zero; break-even = first quarter with positive net cash.
Equity multiple | Money received ÷ money invested. | 2.0x = you get back double.
ROCE / CAGR | Annual return on the initial investment / compound annual growth of the investment.
CLP | Construction Linked Plan – customers pay in instalments as construction progresses. | 10% booking, 10% ATS, slabs …
ATS | Agreement to Sell – usually the second instalment.
Catch-up | A late buyer pays all milestones already reached in one go. | Lag set in Section 8.
S-curve | Slow–fast–slow spending/progress; cumulative graph looks like an S. | Typical for construction.
JV / LO | Joint Venture with a Landowner, who receives a share of revenue instead of cash for land. | LO 32% / developer 68%.
DLC rate | Government circle rate used for stamp duty.
BAR / Premium FAR | Charge for building more than the free FAR allows. | Extra BAR × reserved price × %.
AIF | Alternative Investment Fund – financing cost if land is AIF-funded. | Principal × [(1 + r/m)^(m×t) − 1].
Receivables | Sales booked but not yet paid by customers.
PART 10. CHECKLIST BEFORE SHARING ANY RESULT
✓ | Check
☐ | Status at top of INPUTS = '✔ ALL CHECKS PASSED' (not ✖ or ⚠).
☐ | Active scenario = Base Case (unless you are intentionally showing another scenario).
☐ | Project type and deal type are correct.
☐ | All active products show OK; Plain-English timing sentences in 5B match your intention.
☐ | Each product uses the right payment plan; plans total 100%.
☐ | Tax, stamp duty, BAR %, cost of equity and benchmarks confirmed by Finance.
☐ | STRESS levers at neutral and tables refreshed (F9).
☐ | Quick sanity check: ₹/sq ft and % of GDV of each cost head look reasonable.
☐ | File saved with project name and version (e.g. _v2) – master template untouched.
PART 11. LIMITS OF THE MODEL
Item | Limit | What happens if exceeded
Products | 10 rows | Add more only via the model owner.
Payment plans | 6 plans × 30 milestones | Use blank slots; ask model owner for more.
Booking-linked lag | 0–12 quarters after booking | Plan shows ERROR.
Timeline | 40 quarters (10 years) | 'Project fits inside model horizon' = ERROR.
Cost heads | 21 standard + 3 spare | Use spare rows.
Post-tax IRR | Indicative (tax spread with collections) | Use pre-tax IRR as the headline.
Software | Microsoft Excel (desktop) | STRESS tables blank elsewhere.
Sample data in the template ('Project Aurora') is illustrative only. Replace every input with verified project data before any real decision.