## README
REAL ESTATE FEASIBILITY ENGINE
What it is | An adaptive feasibility model: describe the project with rules (quarters, curves, payment plans) and the engine builds every quarter itself.
Sheets | DASHBOARD (one-page summary) → STRESS (live what-if tables) → INPUTS (everything you type) → TIMELINE (calendar, Gantt & on/off flags) → CURVES (quarterly % for sales, construction & every cost head) → COLLECTIONS (bookings → CLP cash received) → CASHFLOW (outflows, net cash, IRR, NPV) → OUTPUT (revenue, cost, P&L, JV split, key metrics) → LISTS (dropdown sources & conversions).
HOW TO USE
1. Type only in inputs | Blue-on-yellow cells. Black cells are formulas – never overwrite them.
2. Quarters | All timing is a quarter number from the project start (Q1). Type 3 → shows Q3.
3. Products | One row per product with zone and category. Category decides which construction cost head it lands in. Project type (Villa / Apartments / Plotted / Mixed) automatically switches off products of other zones.
4. Product timing | Section 5B: each product's launch and construction start can be a fixed quarter, or linked to another product's launch / sales end / construction start / 50% / end.
5. Cost heads | All 21 standard heads + 3 spare rows. Each has an Applicable switch, its own calculation and a phasing curve.
6. Payment plans | Milestones tied to booking or construction %, so they move automatically with the schedule.
7. Scenarios | One dropdown switches Best / Base / Worst case.
8. Checks | INPUTS must show ✔ ALL CHECKS PASSED before results are used.
9. Stress tests | STRESS sheet tables re-run the whole model automatically. If Excel is slow: Formulas → Calculation Options → Automatic except for Data Tables, then F9.
COLOUR CODE
Blue on yellow | Input
Black | Formula
Green | Link from another sheet
ROADMAP
Step 1 ✔ | Inputs, cost heads, calculators, output statements
Step 2 ✔ | Timeline engine (TIMELINE sheet: 40 self-switching quarter columns + Gantt)
Step 3 ✔ | Curve engine (CURVES sheet: curve names → quarterly %, always 100%)
Step 4 ✔ | COLLECTIONS sheet: bookings, CLP milestone triggers, catch-up, collections, LO/developer split
Step 5 ✔ | CASHFLOW sheet: outflows, landowner payments, project & developer cash flow, IRR, NPV, peak investment, break-even, FY summary
Step 6 ✔ | DASHBOARD sheet: KPI tiles with benchmark colours, auto-written takeaways, 6 charts incl. Gantt
Step 7 ✔ | STRESS sheet: scenario comparison, price / cost / speed / delay sensitivities, 2-way grids, headroom
Disclaimer | Illustrative sample figures. Tax, stamp duty, BAR and regulatory rates must be verified before real use.

## DASHBOARD
Project Aurora (Sample) — FEASIBILITY DASHBOARD
Sample City, Rajasthan ¦ Mixed Development ¦ JV deal ¦ Scenario: Base Case ¦ 6.2 acres, 920,000 sq ft saleable ¦ Jun 2027 – Mar 2032
✔ ALL CHECKS PASSED
GDV (total revenue) |  |  | Total cost |  | EBITDA | PAT
803 |  |  | 630.6053 |  | 172.3947 | 127.5721
₹ 8,728 per sq ft |  |  | 78.5% of GDV |  | 21.5% margin · benchmark 20% | 15.9% margin · tax 26.0%
Developer IRR (pre-tax) |  |  | Project IRR |  | Developer NPV | Equity multiple
110.2% |  |  | 449.1% |  | 90.6281 | 1.4733
Benchmark 18% · post-tax ≈ 84% |  |  | Benchmark 22% · before landowner share |  | @ 18% cost of equity | Benchmark 2.0x · cash multiple 4.4x
Peak investment |  |  | Payback (developer) |  | ROCE (annualised) | CAGR
34.2873 |  |  | Q8 |  | 120.1% | 40.34%
Reached in Q2 (Sep 27) |  |  | Mar 2029 · first +ve quarter Q3 |  | Benchmark 30% · on initial investment | Benchmark 30% · over 5.0 yrs
Green = beats the benchmark set in INPUTS Section 9; amber = review.
KEY TAKEAWAYS (auto-written from the model)
1. The project generates ₹803 Cr of revenue against ₹631 Cr of cost – EBITDA ₹172 Cr (21.5%) and PAT ₹128 Cr (15.9%).
2. The developer earns a pre-tax IRR of 110% against an 18% hurdle, with an NPV of ₹90.6 Cr at the 18% cost of equity.
3. Maximum funding needed is ₹34.3 Cr (Q2); the developer gets all of it back by Q8 (Mar 2029) – construction is largely funded by customer collections.
4. The landowner receives ₹257.0 Cr (32% revenue share) – about ₹85,653 per sq yd, 43% above today's market rate – paid out of collections after his ₹18.0 Cr advance is recovered.
CHART DATA (linked – do not edit)
Cost group | ₹ Cr
Land / landowner share | 259.9807
Construction | 270.4
Marketing & sales | 56.21
Corporate overheads | 32.12
Approvals, legal & BAR | 10.0546
Other (EWS, contingency, EDC, GST, AIF…) | 1.84
Revenue by type | ₹ Cr
Residential | 725
Commercial | 42
Studio | 36
Institutional | 0
EWS / LIG area | 0
Timeline (Gantt) – included products only | Offset | Selling | Building | # included up to row
Villas – selling | 2 | 8 | 0 | 1
Villas – building | 3 | 0 | 12 | 2
Apartments – Towers A & B – selling | 3 | 12 | 0 | 3
Apartments – Towers A & B – building | 4 | 0 | 16 | 4
Studios – selling | 5 | 8 | 0 | 4
Studios – building | 5 | 0 | 12 | 4
High-street retail – selling | 7 | 8 | 0 | 4
High-street retail – building | 5 | 0 | 12 | 4
| 0 | 0 | 0 | 4
| 0 | 0 | 0 | 4
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0
| 0 | 0 | 0

## STRESS
STRESS TESTING — how the deal holds up when things go wrong
Tables below are live Excel Data Tables: each cell re-runs the WHOLE model with the lever value shown. Keep the levers at neutral – the tables flex them automatically.
If Excel feels slow: Formulas → Calculation Options → 'Automatic except for Data Tables', then press F9 to refresh the tables.
A. STRESS LEVERS (inputs – keep at neutral: 0%, 0%, 1.00x, 0, 0)
Lever | Value | Neutral | What it does
Sales price shock | 0% | 0% | Changes every product's sales rate (on top of the scenario)
Construction cost shock | 0% | 0% | Changes every product's construction rate
Sales period multiplier | 1 | 1.00x | 1.5x = every product takes 50% longer to sell
Extra delay (quarters) | 0 | 0 | Pushes every fixed launch & construction start later
Scenario override (0 = use INPUTS) | 0 | 0 | 1 = Best, 2 = Base, 3 = Worst – used by the scenario table
Output selector (technical – keep 1) | 1 | 1 | Lets one table show several outputs; does not change the model
Levers status | Neutral
B. SCENARIO COMPARISON – Best / Base / Worst side by side (scenario table in INPUTS Section 3)
Current model → | 803 | 630.6053 | 110.2% | 90.6281 | 127.5721 | 15.89% | 172.3947 | 34.2873 | Q8 | 1.4733
Scenario # | GDV (₹ Cr) | Total cost (₹ Cr) | Developer IRR | Developer NPV (₹ Cr) | PAT (₹ Cr) | PAT margin | EBITDA (₹ Cr) | Peak investment (₹ Cr) | Payback | Equity multiple
803 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 843.15 | 647.8698 | 150.8% | 111.4557 | 144.5073 | 17.14% | 195.2802 | 34.4479 | Q7 | 1.5287
2 | 803 | 630.6053 | 110.2% | 90.6281 | 127.5721 | 15.89% | 172.3947 | 34.2873 | Q8 | 1.4733
3 | 742.775 | 624.9886 | 40.24% | 35.7674 | 87.162 | 11.73% | 117.7864 | 36.3602 | Q18 | 1.3144
C1. PRICE SENSITIVITY – sales price shock
Current model → | 110.2% | 90.6281 | 127.5721 | 15.89% | 172.3947 | 34.2873 | Q8
Lever value | Developer IRR | Developer NPV (₹ Cr) | PAT (₹ Cr) | PAT margin | EBITDA (₹ Cr) | Peak investment (₹ Cr) | Payback
110.2% | 1 | 2 | 3 | 4 | 5 | 6 | 7
-15% | 73.1% | 49.2241 | 76.7663 | 11.25% | 103.7382 | 33.8055 | Q10
-10% | 86.15% | 63.0254 | 93.7015 | 12.97% | 126.6237 | 33.9661 | Q8
-5% | 98.47% | 76.8268 | 110.6368 | 14.5% | 149.5092 | 34.1267 | Q8
0% | 110.2% | 90.6281 | 127.5721 | 15.89% | 172.3947 | 34.2873 | Q8
5% | 121.4% | 104.4295 | 144.5073 | 17.14% | 195.2802 | 34.4479 | Q8
10% | 132.1% | 118.2308 | 161.4426 | 18.28% | 218.1657 | 34.6085 | Q8
15% | 142.2% | 132.0164 | 178.3779 | 19.32% | 241.0512 | 34.7691 | Q8
C2. CONSTRUCTION COST SENSITIVITY – cost overrun
Current model → | 110.2% | 90.6281 | 127.5721 | 15.89% | 172.3947 | 34.2873 | Q8
Lever value | Developer IRR | Developer NPV (₹ Cr) | PAT (₹ Cr) | PAT margin | EBITDA (₹ Cr) | Peak investment (₹ Cr) | Payback
110.2% | 1 | 2 | 3 | 4 | 5 | 6 | 7
-5% | 117.8% | 99.0773 | 137.5769 | 17.13% | 185.9147 | 34.2873 | Q8
0% | 110.2% | 90.6281 | 127.5721 | 15.89% | 172.3947 | 34.2873 | Q8
5% | 102.4% | 82.1789 | 117.5673 | 14.64% | 158.8747 | 34.2873 | Q8
10% | 94.41% | 73.7297 | 107.5625 | 13.4% | 145.3547 | 34.2873 | Q8
15% | 86.27% | 65.2805 | 97.5577 | 12.15% | 131.8347 | 34.2873 | Q8
20% | 77.95% | 56.8312 | 87.5529 | 10.9% | 118.3147 | 34.2873 | Q10
C3. SALES SPEED SENSITIVITY – how long products take to sell
Current model → | 110.2% | 90.6281 | 127.5721 | 15.89% | 172.3947 | 34.2873 | Q8
Lever value | Developer IRR | Developer NPV (₹ Cr) | PAT (₹ Cr) | PAT margin | EBITDA (₹ Cr) | Peak investment (₹ Cr) | Payback
110.2% | 1 | 2 | 3 | 4 | 5 | 6 | 7
0.75 | 138.1% | 97.348 | 127.5721 | 15.89% | 172.3947 | 34.2873 | Q8
1 | 110.2% | 90.6281 | 127.5721 | 15.89% | 172.3947 | 34.2873 | Q8
1.25 | 88.15% | 82.7952 | 127.5721 | 15.89% | 172.3947 | 34.3933 | Q10
1.5 | 71.72% | 74.5413 | 127.5721 | 15.89% | 172.3947 | 34.3947 | Q11
2 | 50.62% | 58.5816 | 127.5721 | 15.89% | 172.3947 | 35.3701 | Q16
C4. DELAY SENSITIVITY – approvals / launch slip
Current model → | 110.2% | 90.6281 | 127.5721 | 15.89% | 172.3947 | 34.2873 | Q8
Lever value | Developer IRR | Developer NPV (₹ Cr) | PAT (₹ Cr) | PAT margin | EBITDA (₹ Cr) | Peak investment (₹ Cr) | Payback
110.2% | 1 | 2 | 3 | 4 | 5 | 6 | 7
0 | 110.2% | 90.6281 | 127.5721 | 15.89% | 172.3947 | 34.2873 | Q8
1 | 91.89% | 85.2768 | 127.5721 | 15.89% | 172.3947 | 35.6639 | Q9
2 | 79.18% | 80.1481 | 127.5721 | 15.89% | 172.3947 | 36.9153 | Q10
3 | 69.74% | 75.2331 | 127.5721 | 15.89% | 172.3947 | 38.0579 | Q11
4 | 62.42% | 70.5228 | 127.5721 | 15.89% | 172.3947 | 39.1053 | Q12
6 | 51.75% | 61.6835 | 127.5721 | 15.89% | 172.3947 | 40.9584 | Q14
D1. DEVELOPER IRR – price × construction cost
Down: construction cost shock ¦ Across: price shock
110.2% | -10% | -5% | 0% | 5% | 10%
0% | 86.15% | 98.47% | 110.2% | 121.4% | 132.1%
5% | 77.65% | 90.35% | 102.4% | 113.8% | 124.8%
10% | 68.93% | 82.03% | 94.41% | 106.2% | 117.4%
15% | 59.99% | 73.52% | 86.27% | 98.36% | 109.9%
20% | 50.85% | 64.81% | 77.95% | 90.38% | 102.2%
D2. PAT (₹ Cr) – price × construction cost
Down: construction cost shock ¦ Across: price shock
127.5721 | -10% | -5% | 0% | 5% | 10%
0% | 93.7015 | 110.6368 | 127.5721 | 144.5073 | 161.4426
5% | 83.6967 | 100.632 | 117.5673 | 134.5025 | 151.4378
10% | 73.6919 | 90.6272 | 107.5625 | 124.4977 | 141.433
15% | 63.6871 | 80.6224 | 97.5577 | 114.4929 | 131.4282
20% | 53.6823 | 70.6176 | 87.5529 | 104.4881 | 121.4234
D3. PEAK INVESTMENT (₹ Cr) – sales speed × delay
Down: sales period multiplier ¦ Across: extra delay
34.2873 | 0 | 1 | 2 | 4
0.75 | 34.2873 | 35.6639 | 36.9153 | 39.1053
1 | 34.2873 | 35.6639 | 36.9153 | 39.1053
1.25 | 34.3933 | 35.6934 | 36.9153 | 39.1053
1.5 | 34.3947 | 35.6461 | 36.7887 | 38.7997
2 | 35.3701 | 35.9649 | 36.5237 | 37.8099
E. HEADROOM – how much can go wrong before profit disappears
Price fall that wipes out EBITDA | -37.66% | Price shock (all products) at which EBITDA reaches zero
Construction overrun that wipes out EBITDA | 63.76% | Construction cost shock at which EBITDA reaches zero
Exact because EBITDA moves in a straight line with price and construction cost (read from the tables above).
F. DEVELOPER IRR UNDER EACH STRESS
Base case | 110.2%
Price −10% | 86.15%
Construction cost +10% | 94.41%
Sales 1.5x slower | 71.72%
Delay +2 quarters | 79.18%
Worst Case scenario | 40.24%

## INPUTS
REAL ESTATE FEASIBILITY ENGINE — INPUT SHEET
Amounts in ₹ Crore ¦ Areas in sq ft unless stated ¦ Q1 = project start quarter; all timing inputs are quarter numbers (type 3 → shows Q3)
Legend: | Blue on yellow = input | Black = formula | OK / ERROR
0. MODEL HEALTH
Model status | ✔ ALL CHECKS PASSED
Number of errors | 0
GDV (₹ Cr) | 803
Total cost (₹ Cr) | 630.6053
EBITDA margin | 21.47%
PAT (₹ Cr) | 127.5721
Full statements and key metrics are on the OUTPUT sheet.
1. PROJECT & TIMELINE
Parameter | Value | Unit | Notes
Project name | Project Aurora (Sample) | Text | Dummy project – illustrative figures only
Location | Sample City, Rajasthan | Text
Project type | Mixed Development | List | Villa / Plotted / Apartments / Mixed Development
Project start (quarter-end date) = Q1 | 2027-06-30 | Date | 31-Mar, 30-Jun, 30-Sep or 31-Dec
Deal type | JV | List | JV = landowner revenue share ¦ Outright = land bought for cash
Taxable entity | Company | List | Drives the tax rate (Section 9)
Active scenario | Base Case | List | Section 3
Model horizon (quarters) | 40 | Quarters | Engine length (40 = 10 years). Change only if the engine is extended
Crore divisor | 10000000 | ₹ | 1 Crore = 1,00,00,000 – unit constant
Project lifecycle for ROCE / CAGR – override (optional) |  | Years | Leave blank to use the derived span below
Derived
Horizon end date | 2037-03-31 | Date
Project last active quarter | 20 | Quarter | Latest product sales-end / construction-end
Project last active date | 2032-03-31 | Date
Project span (years) | 5 | Years
Project lifecycle used for ROCE / CAGR | 5 | Years
2. LAND
Parameter | Value | Unit | Notes
Land area | 30000 | Sq yd | As per title / sale deed
Land area | 270000 | Sq ft | Conversion factors in LISTS
Land area | 25083.8208 | Sq m
Land area | 6.1983 | Acres
Land area | 9.9174 | Bigha
Current market rate | 60000 | ₹/sq yd | Put sq yd rate only
DLC rate | 13000 | ₹/sq m | Government guideline value (usually notified per sq m)
DLC rate | 10869.6557 | ₹/sq yd | Converted from ₹/sq m
If JV
JV ratio – Landowner (revenue share) | 32% | % | As per JV / JDA revenue share
JV ratio – Developer | 68% | % | 100% for Outright
Stamp duty + registration – JV (% of DLC value) | 2.75% | % | Verify current state rate
If Outright
Land rate for purchase | 60000 | ₹/sq yd | Negotiated price (often = market rate)
Stamp duty + registration – Outright | 8.8% | % | On higher of DLC value and purchase price. Verify rate
Land payment curve | Upfront | List
Land payment start quarter | 1 | Quarter
Land payment end quarter | 1 | Quarter | Ignored when Upfront
Derived
Land value at market rate | 180 | ₹ Cr
Land value at purchase rate | 180 | ₹ Cr
Land cost (Outright) / LO revenue share (JV) | 256.96 | ₹ Cr | JV: LO % × total revenue ¦ Outright: purchase rate × area
Stamp duty + registration | 0.89675 | ₹ Cr | JV: on DLC value ¦ Outright: on higher of DLC & price
Brokerage base (land value) | 180 | ₹ Cr | Brokerage % is entered in the cost table
Total land cost + stamp duty + brokerage | 259.9807 | ₹ Cr | From cost heads 1–3
Land price check
| ₹ Cr per bigha | ₹ per sq yd | Total for land (₹ Cr)
Current market price | 18.15 | 60000 | 180
Land price being offered to LO | 25.9101 | 85653.3333 | 256.96
Difference / return to the LO | 42.76% | 42.76% | 76.96
JV: what the landowner's revenue share is worth per sq yd vs selling at today's market price.
3. SCENARIOS
Scenario name | Sales period multiplier | Sales price change % | Construction cost change % | Launch & construction delay (quarters) | Row check
Best Case | 0.75 | 5% | 0% | 0 | OK
Base Case | 1 | 0% | 0% | 0 | OK
Worst Case | 1.5 | -7.5% | 7.5% | 2 | OK
Active scenario values (incl. STRESS levers) → | 1 | 0% | 0% | 0
4. DEVELOPMENT ZONES (share of land)
Development zone | Area share % of land | Land area (sq ft) | Saleable area (sq ft) | Revenue (₹ Cr) | In this project type?
Villa Development | 35% | 94500 | 250000 | 275 | Used
Apartment Development | 50% | 135000 | 670000 | 528 | Used
Plotted Development | 15% | 40500 | 0 | 0 | Used
Other / Clubhouse | 0% | 0 | 0 | 0 | Used
TOTAL | 100% | 270000 | 920000 | 803
Total share must not exceed 100%. Saleable area and revenue come from the product mix below.
5. PRODUCT MIX (one row per product – fill a spare row and set 'Include? (your choice)' = Yes in column X)
Column E is automatic: a product is active only if you include it (column X) AND its development zone belongs to the selected Project type (Mixed Development = all zones). Inactive products disappear from every calculation.
Product name | Development zone | Category | Active? (auto: your choice × project type) | Saleable area (sq ft) | Base sales rate (₹/sq ft) | Construction cost (₹/sq ft) | Launch quarter (used if 'Fixed') | Sales period (quarters) | Sales curve | CLP / payment plan | Construction start quarter (used if 'Fixed') | Construction duration (quarters) | Construction curve | Launch Q (after scenario) | Sales end Q | Constr. start Q | Constr. end Q | Revenue (₹ Cr) | Construction cost (₹ Cr) | Launch date | Row check | Include? (your choice)
Villas | Villa Development | Villa | Yes | 250000 | 11000 | 2900 | 3 | 8 | Front-loaded | CLP – Villa | 4 | 12 | S-curve | 3 | 10 | 4 | 15 | 275 | 72.5 | 2027-12-31 | OK | Yes
Apartments – Towers A & B | Apartment Development | Apartment | Yes | 600000 | 7500 | 2900 | 4 | 12 | Even | CLP – Apartment | 5 | 16 | S-curve | 4 | 15 | 5 | 20 | 450 | 174 | 2028-03-31 | OK | Yes
Studios | Apartment Development | Studio | Yes | 40000 | 9000 | 3800 | 6 | 8 | Even | CLP – Apartment | 6 | 12 | S-curve | 6 | 13 | 6 | 17 | 36 | 15.2 | 2028-09-30 | OK | Yes
High-street retail | Apartment Development | Commercial | Yes | 30000 | 14000 | 2900 | 8 | 8 | Back-loaded | Down Payment Plan | 6 | 12 | S-curve | 8 | 15 | 6 | 17 | 42 | 8.7 | 2029-03-31 | OK | Yes
Residential plots | Plotted Development | Plot | No | 150000 | 4500 | 450 | 10 | 8 | Even | Plot – Development Linked | 9 | 8 | Even |  |  |  |  | 0 | 0 |  | Off | No
Institutional plots | Plotted Development | Institutional | No | 30000 | 4000 | 400 | 12 | 8 | Even | Plot – Development Linked | 9 | 8 | Even |  |  |  |  | 0 | 0 |  | Off | No
EWS / LIG plots | Plotted Development | EWS/LIG | No | 20000 | 1500 | 400 | 10 | 8 | Even | Plot – Development Linked | 9 | 8 | Even |  |  |  |  | 0 | 0 |  | Off | No
|  |  | No | [14 empty] | 0 | 0 |  | Off | No
|  |  | No | [14 empty] | 0 | 0 |  | Off | No
|  |  | No | [14 empty] | 0 | 0 |  | Off | No
TOTAL (included products) |  |  |  | 920000 | 8728.2609 | 2939.1304 | [11 empty] | 803 | 270.4
Totals row shows weighted-average rates. Revenue is before price escalation. Zone 'Plotted Development' revenue attracts the plotted marketing rate.
5B. PRODUCT TIMING – how each product's launch and construction start are decided
Fixed quarter = uses the quarter typed in Section 5. Linked = X quarters after an event of another product listed ABOVE it (put your lead product first).
Offset 0 = same quarter as the event; 1 = next quarter; −1 = one quarter before. Scenario delay is applied once, to fixed quarters only – linked products inherit it.
Product | Launch timing | Launch – linked product | Launch – linked event | Launch offset (quarters) | Construction timing | Construction – linked product | Construction – linked event | Construction offset (quarters) | Constr. start (pre-calc) | Launch Q (final) | Constr. start Q (final) | Row check | Plain-English result
Villas | Fixed quarter |  |  |  | After own launch |  |  | 1 |  | 3 | 4 | OK | Launch Q3 (fixed) ¦ Construction Q4 (1 qtr(s) after own launch)
Apartments – Towers A & B | Linked to another product | Villas | Launch | 1 | After own launch |  |  | 1 |  | 4 | 5 | OK | Launch Q4 (1 qtr(s) after Villas – launch) ¦ Construction Q5 (1 qtr(s) after own launch)
Studios | Linked to another product | Apartments – Towers A & B | Construction start | 1 | After own launch |  |  | 0 |  | 6 | 6 | OK | Launch Q6 (1 qtr(s) after Apartments – Towers A & B – construction start) ¦ Construction Q6 (0 qtr(s) after own launch)
High-street retail | Linked to another product | Apartments – Towers A & B | Launch | 4 | Linked to another product | Apartments – Towers A & B | Construction start | 1 | 6 | 8 | 6 | OK | Launch Q8 (4 qtr(s) after Apartments – Towers A & B – launch) ¦ Construction Q6 (1 qtr(s) after Apartments – Towers A & B – construction start)
Residential plots | Fixed quarter |  |  |  | Fixed quarter |  |  |  | 9 | 10 | 9 | Off | —
Institutional plots | Fixed quarter |  |  |  | Fixed quarter |  |  |  | 9 | 12 | 9 | Off | —
EWS / LIG plots | Fixed quarter |  |  |  | Fixed quarter |  |  |  | 9 | 10 | 9 | Off | —
(row 8) | Fixed quarter |  |  |  | Fixed quarter | [6 empty] | Off | —
(row 9) | Fixed quarter |  |  |  | Fixed quarter | [6 empty] | Off | —
(row 10) | Fixed quarter |  |  |  | Fixed quarter | [6 empty] | Off | —
Tip: a product can only link to a product listed above it – this rule makes circular links impossible.
Summarised view (included products)
Area type | Sq ft | Sq yd | Bigha | Revenue (₹ Cr)
Residential saleable area | 850000 | 94444.4444 | 31.2213 | 725
Commercial saleable area | 30000 | 3333.3333 | 1.1019 | 42
Studio saleable area | 40000 | 4444.4444 | 1.4692 | 36
Institutional saleable area | 0 | 0 | 0 | 0
EWS / LIG area | 0 | 0 | 0 | 0
Total saleable area | 920000 | 102222.2222 | 33.7925 | 803
6. COST HEADS (each head: how it is calculated + when it is spent)
Cost head | How it is calculated | Rate / input 1 | Input 2 | Applicable? | Amount (₹ Cr) | ₹ per sq ft (saleable) | % of total revenue | Phasing curve | Start quarter | End quarter | Row check | Notes
Land Cost | JV: LO share × total revenue ¦ Outright: rate × area | Auto |  | Yes | 256.96 | 2793.0435 | 32% | Follow Collections |  |  | OK | Section 2. JV: LO is paid his share of each collection
Stamp Duty | JV: DLC value × JV % ¦ Outright: higher of DLC/price × % | Auto |  | Yes | 0.89675 | 9.7472 | 0.1117% | Upfront | 1 | 1 | OK | Paid at JDA / sale deed registration
Brokerage | % (incl. GST) × land value | 1.18% |  | Yes | 2.124 | 23.087 | 0.2645% | Upfront | 1 | 1 | OK | e.g. 1% + 18% GST = 1.18%. JV: on market value ¦ Outright: on price
Villa Construction Cost | Σ Villa products: area × ₹/sq ft | 2900 |  | Yes | 72.5 | 788.0435 | 9.029% | Follow Construction |  |  | OK | Structure + finishes + MEP + clubhouse
APT Construction Cost | Σ Apartment products: area × ₹/sq ft | 2900 |  | Yes | 174 | 1891.3043 | 21.67% | Follow Construction |  |  | OK | Depends on height & type of development
Studio Construction cost with furnishing | Σ Studio products: area × ₹/sq ft | 3800 |  | Yes | 15.2 | 165.2174 | 1.893% | Follow Construction |  |  | OK | Rate in product table already includes furnishing (e.g. 3,000 + 800)
Plotted Construction Development Cost | Σ Plot products: area × ₹/sq ft | 0 |  | Yes | 0 | 0 | 0% | Follow Construction |  |  | OK | Services + clubhouse
Institutional Plotted Development Cost | Σ Institutional products: area × ₹/sq ft | 0 |  | Yes | 0 | 0 | 0% | Follow Construction |  |  | OK
Commercial Construction Cost | Σ Commercial products: area × ₹/sq ft | 2900 |  | Yes | 8.7 | 94.5652 | 1.083% | Follow Construction |  |  | OK | Take rate as per type of commercial
EWS/LIG plots development cost | Σ EWS/LIG products: area × ₹/sq ft | 0 |  | Yes | 0 | 0 | 0% | Follow Construction |  |  | OK
Corporate Overheads (₹/Sq Ft SA) | % × total revenue | 4% |  | Yes | 32.12 | 349.1304 | 4% | Follow Project Life |  |  | OK | RO + HO charges (typically 4%–6% of revenue)
Marketing & Sales @ % | Input 1 % × built-up revenue + Input 2 % × plotted revenue | 7% | 5% | Yes | 56.21 | 610.9783 | 7% | Follow Sales |  |  | OK | 7% of built-up & 5% of plotted revenue
Legal & Compliance (₹/Sq Ft SA) | ₹/sq ft × total saleable area | 75 |  | Yes | 6.9 | 75 | 0.8593% | Front-loaded | 1 | 8 | OK | Approvals, land conversion & compliance
EWS / LIG @ ₹/Sq Ft (Builtup) | Loss ₹/sq ft (Input 1) × EWS share of SA (Input 2) × total SA | 400 | 5% | Yes | 1.84 | 20 | 0.2291% | Follow Construction |  |  | OK | Mandatory EWS @ 5% of saleable area; loss ~₹400/sq ft
Contingency @ % | % (Input 1) × base chosen in Input 2 | 0% | Construction cost | Yes | 0 | 0 | 0% | Follow Construction |  |  | OK | Buffer for overruns. Base excludes land heads & contingency itself
External Development & Landscaping | Input 1 applied as per basis chosen in Input 2 | 0 | ₹/sq ft (total saleable area) | Yes | 0 | 0 | 0% | Follow Construction |  |  | OK | Roads, landscaping & external services
Hotel Brand Key fee ₹50K per Key for smaller brand | Fee per key (₹) × number of keys | 50000 | 0 | Yes | 0 | 0 | 0% | Follow Construction |  |  | OK | Enter number of keys in Input 2 (0 = not applicable)
Furnishing Cost for Studios | ₹/sq ft × studio saleable area | 500 |  | No | 0 | 0 | 0% | Follow Construction |  |  | OK | Keep 'No' if furnishing is already in the studio construction rate (avoid double counting)
GST cost in case of commercial/Plotting development | Commercial + plot revenue × unsold % (Input 2) × GST % (Input 1) × developer share | 18% | 20% | No | 0 | 0 | 0% | At Project End |  |  | OK | GST on unsold inventory at completion. Switched off by default
AIF Cost | Calculator in Section 7B | Auto |  | No | 0 | 0 | 0% | Follow Project Life |  |  | OK | Switched off by default – set 'Yes' if land is AIF-funded
BAR / Premium FAR Cost | Calculator in Section 7A | Auto |  | Yes | 3.1546 | 34.2889 | 0.3928% | Upfront | 2 | 2 | OK | Paid at approval stage
[5 empty] | 0 | 0 | 0% |  |  |  |  | Spare row – add any other cost head here
[5 empty] | 0 | 0 | 0% |  |  |  |  | Spare row – add any other cost head here
[5 empty] | 0 | 0 | 0% |  |  |  |  | Spare row – add any other cost head here
TOTAL COST |  |  |  |  | 630.6053 | 6854.4057 | 78.53%
Total development cost (construction heads) |  |  |  |  | 270.4
Construction heads pick up every product by its Category. Start/End quarters are needed only for Upfront, Even, Front-loaded, Back-loaded and S-curve.
7. CALCULATORS (BAR / premium FAR, AIF cost, initial investment)
7A. BAR / Premium FAR cost
Parameter | Value | Unit | Notes
Authority | JDA | List | RIICO or JDA – picks the % from the table below
Land use | Residential | List
Free FAR / BAR (× land area) | 2 | × | Free BAR area = land area (sq m) × this
Loading factor (saleable ÷ planned BUA) | 1.35 | × | Planned area = saleable area ÷ this
BAR reserved price | 12000 | ₹/sq m | As notified by the authority
GST on BAR applicable? | No | List | Typically Yes for RIICO land
GST rate on BAR | 18% | %
BAR reserved price % table
Land use | RIICO | JDA
Industrial | 20%
Residential | 30% | 20%
Commercial | 40% | 40%
Derived
Free BAR area | 50167.6416 | Sq m
Planned development area | 63311.7013 | Sq m | Total saleable area (sq ft → sq m) ÷ loading
Extra BAR area | 13144.0597 | Sq m | Zero if planned area is within free FAR
Applicable reserved price % | 20% | % | Blank in table = combination not allowed → ERROR
BAR cost (excl. GST) | 3.1546 | ₹ Cr | Extra BAR × reserved price × %
BAR cost used in model | 3.1546 | ₹ Cr | Incl. GST if applicable
7B. AIF cost
Parameter | Value | Unit | Notes
Principal (land cost + stamp duty + brokerage) | 259.9807 | ₹ Cr | Linked from land heads
Interest rate (annual) | 18% | %
Tenure | 3 | Years
Compounding | Annually | List
Compounding periods per year | 1 | No.
AIF cost (interest) | 167.1759 | ₹ Cr | Principal × [(1 + r/m)^(m × t) − 1]
7C. Initial investment – JV (outlay till DA / conveyance)
Advance to LO (% of land value at market) | 10% | % | 10% standard; negotiable at DA
Item | How calculated | Amount (₹ Cr) | Payout quarter | Remarks
Term sheet token | Total advance − DD − DA instalments | 18 | 1 | Balancing figure
On completion of due diligence | Input | 0 | 1
Advance to LO at DA | Input | 0 | 2
Approval cost / legal & compliance | Legal head × % (Input in C) | 6.9 | 2
Development cost (pre-DA) | Input | 0 | 2 | Depends on project size, type & city
Marketing cost (pre-launch) | Input | 0 | 2 | Depends on project size, type & city
Stamp duty | Linked: cost head | 0.89675 | 2
Brokerage | Linked: cost head | 2.124 | 2
BAR cost (upfront share) | BAR head × % (Input in C) | 0.78864 | 2 | Part of BAR paid upfront
Share of legal & compliance paid before DA | 100% | %
Share of BAR cost paid upfront | 25% | % | e.g. 1/4 in Jaipur
Initial investment – JV (total) | 28.7094 | ₹ Cr
7D. Initial investment – Outright
Share of built-up construction (villa + apt + studio) in initial outlay | 10% | %
Share of legal & compliance in initial outlay | 10% | %
Initial investment – Outright (total) | 286.8407 | ₹ Cr | Land + SD + brokerage + shares above
INITIAL INVESTMENT USED | 28.7094 | ₹ Cr | Picked by deal type
Step 5 note: stamp duty, brokerage, legal and BAR here are the early timing of those cost heads (not extra cost); the LO advance is recovered from the LO's share.
8. CLP / PAYMENT PLAN LIBRARY (milestones tied to booking or construction %)
Booking + quarters: due that many quarters after booking (0 = at booking). Construction % complete: due when that product's construction reaches the %.
Late buyers pay all milestones already reached in one go (catch-up). Each plan must total exactly 100%. Each plan holds up to 30 milestones and there are 6 plan slots – adding milestones needs NO change anywhere else.
Parameter | Value | Unit | Notes
Catch-up payment lag (quarters after booking) | 1 | Quarters | Late buyers pay construction milestones already reached this many quarters after booking (1 = together with ATS, 0 = at booking)
Plan name → | CLP – Villa | Up to 30 milestones – just fill the next empty row. Booking-linked lag max 12 quarters.
Milestone | Trigger type | Trigger value | % of sale value | Cumulative % | Row check
Earnest money | Booking + quarters | 0 | 10% | 10% | OK
Agreement to sell (ATS) | Booking + quarters | 1 | 10% | 20% | OK
Commencement of construction | Construction % complete | 0.05 | 10% | 30% | OK
Ground plinth | Construction % complete | 0.15 | 10% | 40% | OK
First floor roof casting | Construction % complete | 0.35 | 15% | 55% | OK
Second floor roof casting | Construction % complete | 0.55 | 15% | 70% | OK
Third floor roof casting | Construction % complete | 0.75 | 15% | 85% | OK
Completion certificate (CC) | Construction % complete | 0.95 | 5% | 90% | OK
Possession | Construction % complete | 1 | 10% | 100% | OK
Plan total & status |  |  | 100% |  | OK
Plan name → | CLP – Apartment | Up to 30 milestones – just fill the next empty row. Booking-linked lag max 12 quarters.
Milestone | Trigger type | Trigger value | % of sale value | Cumulative % | Row check
Booking amount | Booking + quarters | 0 | 10% | 10% | OK
Agreement to sell (ATS) | Booking + quarters | 1 | 10% | 20% | OK
Foundation completion | Construction % complete | 0.1 | 10% | 30% | OK
Podium / plinth | Construction % complete | 0.2 | 10% | 40% | OK
Slab casting – 25% floors | Construction % complete | 0.35 | 10% | 50% | OK
Slab casting – 50% floors | Construction % complete | 0.5 | 10% | 60% | OK
Slab casting – 75% floors | Construction % complete | 0.65 | 10% | 70% | OK
Top slab casting | Construction % complete | 0.8 | 10% | 80% | OK
Brickwork & plaster | Construction % complete | 0.9 | 5% | 85% | OK
Flooring & finishing | Construction % complete | 0.95 | 5% | 90% | OK
Possession | Construction % complete | 1 | 10% | 100% | OK
Plan total & status |  |  | 100% |  | OK
Plan name → | Plot – Development Linked | Up to 30 milestones – just fill the next empty row. Booking-linked lag max 12 quarters.
Milestone | Trigger type | Trigger value | % of sale value | Cumulative % | Row check
Booking amount | Booking + quarters | 0 | 10% | 10% | OK
Agreement to sell (ATS) | Booking + quarters | 1 | 20% | 30% | OK
Roads & services start | Construction % complete | 0.25 | 20% | 50% | OK
Services 60% complete | Construction % complete | 0.6 | 20% | 70% | OK
Possession / registry | Construction % complete | 1 | 30% | 100% | OK
Plan total & status |  |  | 100% |  | OK
Plan name → | Down Payment Plan | Up to 30 milestones – just fill the next empty row. Booking-linked lag max 12 quarters.
Milestone | Trigger type | Trigger value | % of sale value | Cumulative % | Row check
Booking amount | Booking + quarters | 0 | 10% | 10% | OK
Down payment | Booking + quarters | 1 | 80% | 90% | OK
Possession | Construction % complete | 1 | 10% | 100% | OK
Plan total & status |  |  | 100% |  | OK
Plan name → | CLP – 17-Floor Tower | Up to 30 milestones – just fill the next empty row. Booking-linked lag max 12 quarters.
Milestone | Trigger type | Trigger value | % of sale value | Cumulative % | Row check
Booking amount | Booking + quarters | 0 | 10% | 10% | OK
Agreement to sell (ATS) | Booking + quarters | 1 | 10% | 20% | OK
Excavation | Construction % complete | 0.03 | 5% | 25% | OK
Foundation / raft | Construction % complete | 0.08 | 5% | 30% | OK
Slab casting – floor 1 | Construction % complete | 0.12 | 2.5% | 32.5% | OK
Slab casting – floor 2 | Construction % complete | 0.15625 | 2.5% | 35% | OK
Slab casting – floor 3 | Construction % complete | 0.1925 | 2.5% | 37.5% | OK
Slab casting – floor 4 | Construction % complete | 0.22875 | 2.5% | 40% | OK
Slab casting – floor 5 | Construction % complete | 0.265 | 2.5% | 42.5% | OK
Slab casting – floor 6 | Construction % complete | 0.30125 | 2.5% | 45% | OK
Slab casting – floor 7 | Construction % complete | 0.3375 | 2.5% | 47.5% | OK
Slab casting – floor 8 | Construction % complete | 0.37375 | 2.5% | 50% | OK
Slab casting – floor 9 | Construction % complete | 0.41 | 2.5% | 52.5% | OK
Slab casting – floor 10 | Construction % complete | 0.44625 | 2.5% | 55% | OK
Slab casting – floor 11 | Construction % complete | 0.4825 | 2.5% | 57.5% | OK
Slab casting – floor 12 | Construction % complete | 0.51875 | 2.5% | 60% | OK
Slab casting – floor 13 | Construction % complete | 0.555 | 2.5% | 62.5% | OK
Slab casting – floor 14 | Construction % complete | 0.59125 | 2.5% | 65% | OK
Slab casting – floor 15 | Construction % complete | 0.6275 | 2.5% | 67.5% | OK
Slab casting – floor 16 | Construction % complete | 0.66375 | 2.5% | 70% | OK
Slab casting – floor 17 | Construction % complete | 0.7 | 2.5% | 72.5% | OK
Brickwork | Construction % complete | 0.78 | 5% | 77.5% | OK
Plaster & MEP | Construction % complete | 0.85 | 5% | 82.5% | OK
Flooring & finishing | Construction % complete | 0.92 | 7.5% | 90% | OK
Possession | Construction % complete | 1 | 10% | 100% | OK
Plan total & status |  |  | 100% |  | OK
Plan name → |  | Up to 30 milestones – just fill the next empty row. Booking-linked lag max 12 quarters.
Milestone | Trigger type | Trigger value | % of sale value | Cumulative % | Row check
Plan total & status |  |  | 0% |  | Unused
9. TAX, RETURNS & KPI BENCHMARKS
Parameter | Value | Unit | Notes
Tax rate – Company | 26% | % | As per existing model (statutory 115BAA: 25.17%). Verify with Finance
Tax rate – LLP | 35% | % | As per existing model (statutory: 34.94%). Verify with Finance
Applied tax rate | 26% | %
Cost of equity / discount rate | 18% | % | Used for NPV and as developer IRR hurdle
KPI benchmarks (Status shows ✅ Strong if metric beats benchmark)
Project IRR | 22% | %
Developer IRR | 18% | % | Cost of equity
Equity multiple | 2 | x
ROCE (annualised) | 30% | % | Should exceed cost of borrowing
CAGR | 30% | %
PAT margin | 15% | % | Ideally > 15% for large-scale development
EBITDA margin | 20% | % | Group housing target > 20%
10. MODEL CHECKS (all must be OK)
Check | Result | What to fix if ERROR
Project start is a valid quarter-end date | OK | Enter 31-Mar, 30-Jun, 30-Sep or 31-Dec
Project type, deal type & entity selected | OK | Pick from dropdowns
Lifecycle override valid (if used) | OK | Blank or a positive number of years
Scenario table valid & active scenario exists | OK | Section 3
Land inputs valid | OK | Area & rates > 0; JV share 0%–99.9%
Zone shares total ≤ 100% | OK | Section 4
At least one product active for the project type | OK | Include a product whose zone matches the Project type
All included products valid | OK | Section 5 rows marked ERROR
Product names unique (needed for links) | OK | Give every product row a different name
Product timing links valid | OK | Section 5B rows marked ERROR (link must point to an included product above)
All payment plans total 100% & valid | OK | Section 8
All cost rows valid | OK | Section 6 rows marked ERROR
Construction heads reconcile to product table | OK | Every product category must map to a construction head
BAR calculator valid | OK | Authority/land-use combination must have a % in the table
AIF calculator valid | OK | Rate ≥ 0, tenure ≥ 0
Initial investment valid | OK | DD + DA ≤ total advance; payout quarters whole numbers 1–horizon
Project fits inside model horizon | OK | Shorten timeline or extend engine
Tax, cost of equity & benchmarks valid | OK | Enter numbers; tax < 100%
Cash flow engine consistent | OK | See checks at the bottom of the CASHFLOW sheet
Collections engine consistent | OK | See checks at the bottom of the COLLECTIONS sheet
Catch-up lag valid (0–4 whole quarters) | OK | Section 8
Curve engine consistent | OK | See checks at the bottom of the CURVES sheet
Timeline engine consistent | OK | See checks at the bottom of the TIMELINE sheet
Formulas:
Launch date = IF(AND([OK / ERROR]="Yes",ISNUMBER([Launch Q (after scenario)])),EOMONTH(C20,3*([Launch Q (after scenario)]-1)),"")

## TIMELINE
TIMELINE ENGINE — 40 quarters that switch themselves on and off
Timeline engine status | OK
No inputs on this sheet. Every cell reads the INPUTS sheet, so changing a date, duration or scenario re-draws everything here.
A. QUARTER CALENDAR
Quarter number |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Quarter label |  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 | Q17 | Q18 | Q19 | Q20 | Q21 | Q22 | Q23 | Q24 | Q25 | Q26 | Q27 | Q28 | Q29 | Q30 | Q31 | Q32 | Q33 | Q34 | Q35 | Q36 | Q37 | Q38 | Q39 | Q40
Quarter end date |  | 2027-06-30 | 2027-09-30 | 2027-12-31 | 2028-03-31 | 2028-06-30 | 2028-09-30 | 2028-12-31 | 2029-03-31 | 2029-06-30 | 2029-09-30 | 2029-12-31 | 2030-03-31 | 2030-06-30 | 2030-09-30 | 2030-12-31 | 2031-03-31 | 2031-06-30 | 2031-09-30 | 2031-12-31 | 2032-03-31 | 2032-06-30 | 2032-09-30 | 2032-12-31 | 2033-03-31 | 2033-06-30 | 2033-09-30 | 2033-12-31 | 2034-03-31 | 2034-06-30 | 2034-09-30 | 2034-12-31 | 2035-03-31 | 2035-06-30 | 2035-09-30 | 2035-12-31 | 2036-03-31 | 2036-06-30 | 2036-09-30 | 2036-12-31 | 2037-03-31
Quarter start date |  | 2027-04-01 | 2027-07-01 | 2027-10-01 | 2028-01-01 | 2028-04-01 | 2028-07-01 | 2028-10-01 | 2029-01-01 | 2029-04-01 | 2029-07-01 | 2029-10-01 | 2030-01-01 | 2030-04-01 | 2030-07-01 | 2030-10-01 | 2031-01-01 | 2031-04-01 | 2031-07-01 | 2031-10-01 | 2032-01-01 | 2032-04-01 | 2032-07-01 | 2032-10-01 | 2033-01-01 | 2033-04-01 | 2033-07-01 | 2033-10-01 | 2034-01-01 | 2034-04-01 | 2034-07-01 | 2034-10-01 | 2035-01-01 | 2035-04-01 | 2035-07-01 | 2035-10-01 | 2036-01-01 | 2036-04-01 | 2036-07-01 | 2036-10-01 | 2037-01-01
Period |  | Apr–Jun 27 | Jul–Sep 27 | Oct–Dec 27 | Jan–Mar 28 | Apr–Jun 28 | Jul–Sep 28 | Oct–Dec 28 | Jan–Mar 29 | Apr–Jun 29 | Jul–Sep 29 | Oct–Dec 29 | Jan–Mar 30 | Apr–Jun 30 | Jul–Sep 30 | Oct–Dec 30 | Jan–Mar 31 | Apr–Jun 31 | Jul–Sep 31 | Oct–Dec 31 | Jan–Mar 32 | Apr–Jun 32 | Jul–Sep 32 | Oct–Dec 32 | Jan–Mar 33 | Apr–Jun 33 | Jul–Sep 33 | Oct–Dec 33 | Jan–Mar 34 | Apr–Jun 34 | Jul–Sep 34 | Oct–Dec 34 | Jan–Mar 35 | Apr–Jun 35 | Jul–Sep 35 | Oct–Dec 35 | Jan–Mar 36 | Apr–Jun 36 | Jul–Sep 36 | Oct–Dec 36 | Jan–Mar 37
Financial year end (Apr–Mar) |  | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031 | 2031 | 2031 | 2032 | 2032 | 2032 | 2032 | 2033 | 2033 | 2033 | 2033 | 2034 | 2034 | 2034 | 2034 | 2035 | 2035 | 2035 | 2035 | 2036 | 2036 | 2036 | 2036 | 2037 | 2037 | 2037 | 2037
Financial year |  | FY 2027-28 | FY 2027-28 | FY 2027-28 | FY 2027-28 | FY 2028-29 | FY 2028-29 | FY 2028-29 | FY 2028-29 | FY 2029-30 | FY 2029-30 | FY 2029-30 | FY 2029-30 | FY 2030-31 | FY 2030-31 | FY 2030-31 | FY 2030-31 | FY 2031-32 | FY 2031-32 | FY 2031-32 | FY 2031-32 | FY 2032-33 | FY 2032-33 | FY 2032-33 | FY 2032-33 | FY 2033-34 | FY 2033-34 | FY 2033-34 | FY 2033-34 | FY 2034-35 | FY 2034-35 | FY 2034-35 | FY 2034-35 | FY 2035-36 | FY 2035-36 | FY 2035-36 | FY 2035-36 | FY 2036-37 | FY 2036-37 | FY 2036-37 | FY 2036-37
Quarter of financial year |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Project year |  | Y1 | Y1 | Y1 | Y1 | Y2 | Y2 | Y2 | Y2 | Y3 | Y3 | Y3 | Y3 | Y4 | Y4 | Y4 | Y4 | Y5 | Y5 | Y5 | Y5 | Y6 | Y6 | Y6 | Y6 | Y7 | Y7 | Y7 | Y7 | Y8 | Y8 | Y8 | Y8 | Y9 | Y9 | Y9 | Y9 | Y10 | Y10 | Y10 | Y10
Within model horizon (1 = yes) | 40 | bar: Q1 to Q4
Project active (1 = yes) | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project phase |  | Pre-launch | Pre-launch | Sales | Sales + Constr. | Sales + Constr. | Sales + Constr. | Sales + Constr. | Sales + Constr. | Sales + Constr. | Sales + Constr. | Sales + Constr. | Sales + Constr. | Sales + Constr. | Sales + Constr. | Sales + Constr. | Construction | Construction | Construction | Construction | Construction | Post-project | Post-project | Post-project | Post-project | Post-project | Post-project | Post-project | Post-project | Post-project | Post-project | Post-project | Post-project | Post-project | Post-project | Post-project | Post-project | Post-project | Post-project | Post-project | Post-project
B. GANTT VIEW (S = selling, C = under construction, S+C = both, ✓ = construction complete)
Villas |  |  |  | S | S+C | S+C | S+C | S+C | S+C | S+C | S+C | C | C | C | C | C | ✓ | ✓ | ✓ | ✓ | ✓
Apartments – Towers A & B |  |  |  |  | S | S+C | S+C | S+C | S+C | S+C | S+C | S+C | S+C | S+C | S+C | S+C | C | C | C | C | C
Studios | [6 empty] | S+C | S+C | S+C | S+C | S+C | S+C | S+C | S+C | C | C | C | C | ✓ | ✓ | ✓
High-street retail | [6 empty] | C | C | S+C | S+C | S+C | S+C | S+C | S+C | S+C | S+C | C | C | ✓ | ✓ | ✓
(product row 5 – off)
(product row 6 – off)
(product row 7 – off)
(product row 8 – off)
(product row 9 – off)
(product row 10 – off)
C. PRODUCT TIMING FLAGS (1 = on; 'Q#' = position inside the window, used by the curve engine)
Count / n
Villas
Sales window (1 = selling) | 8 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales quarter # in window | 8 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction window (1 = building) | 12 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction quarter # in window | 12 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction complete (1 = after end) | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Timing check | OK
Apartments – Towers A & B
Sales window (1 = selling) | 12 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales quarter # in window | 12 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction window (1 = building) | 16 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction quarter # in window | 16 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction complete (1 = after end) | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Timing check | OK
Studios
Sales window (1 = selling) | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales quarter # in window | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction window (1 = building) | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction quarter # in window | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction complete (1 = after end) | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Timing check | OK
High-street retail
Sales window (1 = selling) | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales quarter # in window | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction window (1 = building) | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction quarter # in window | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction complete (1 = after end) | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Timing check | OK
Product row 5 (off)
Sales window (1 = selling) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction window (1 = building) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction complete (1 = after end) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Timing check | Off
Product row 6 (off)
Sales window (1 = selling) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction window (1 = building) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction complete (1 = after end) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Timing check | Off
Product row 7 (off)
Sales window (1 = selling) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction window (1 = building) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction complete (1 = after end) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Timing check | Off
Product row 8 (off)
Sales window (1 = selling) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction window (1 = building) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction complete (1 = after end) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Timing check | Off
Product row 9 (off)
Sales window (1 = selling) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction window (1 = building) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction complete (1 = after end) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Timing check | Off
Product row 10 (off)
Sales window (1 = selling) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction window (1 = building) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction complete (1 = after end) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Timing check | Off
D. COST PHASING WINDOWS (for curve-based heads; 'Follow …' heads are driven by sales / construction / collections)
Count / n
Land Cost | Follow Collections
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
Stamp Duty | Upfront
Window (1 = spend allowed) | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
Brokerage | Upfront
Window (1 = spend allowed) | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
Villa Construction Cost | Follow Construction
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
APT Construction Cost | Follow Construction
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
Studio Construction cost with furnishing | Follow Construction
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
Plotted Construction Development Cost | Follow Construction
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
Institutional Plotted Development Cost | Follow Construction
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
Commercial Construction Cost | Follow Construction
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
EWS/LIG plots development cost | Follow Construction
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
Corporate Overheads (₹/Sq Ft SA) | Follow Project Life
Window (1 = spend allowed) | 20 | 1 | 1 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | bar: S to ✓
Quarter # in window | 20 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
Marketing & Sales @ % | Follow Sales
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
Legal & Compliance (₹/Sq Ft SA) | Front-loaded
Window (1 = spend allowed) | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 8 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
EWS / LIG @ ₹/Sq Ft (Builtup) | Follow Construction
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
Contingency @ % | Follow Construction
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
External Development & Landscaping | Follow Construction
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
Hotel Brand Key fee ₹50K per Key for smaller brand | Follow Construction
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
Furnishing Cost for Studios | Follow Construction
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
GST cost in case of commercial/Plotting development | At Project End
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
AIF Cost | Follow Project Life
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
BAR / Premium FAR Cost | Upfront
Window (1 = spend allowed) | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check | OK
Spare cost row
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check
Spare cost row
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check
Spare cost row
Window (1 = spend allowed) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quarter # in window | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Window check
E. TIMELINE CHECKS
Horizon fits the engine (1 to 40 quarters, whole number) | OK
Quarter numbers run 1, 2, 3 … without gaps | OK
Quarter dates are consecutive quarter-ends | OK
Active quarters = project last active quarter | OK
Every product's windows have the right length | OK
Every cost window has the right length | OK

## CURVES
CURVE ENGINE — turns curve names into quarterly percentages that always add up to 100%
Curve engine status | OK
No inputs here. Each row = share of a total that falls in each quarter. Position (i) and window length (n) come from TIMELINE; the curve name comes from INPUTS.
Quarter | Total | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 | Q17 | Q18 | Q19 | Q20 | Q21 | Q22 | Q23 | Q24 | Q25 | Q26 | Q27 | Q28 | Q29 | Q30 | Q31 | Q32 | Q33 | Q34 | Q35 | Q36 | Q37 | Q38 | Q39 | Q40
Quarter end |  | 2027-06-30 | 2027-09-30 | 2027-12-31 | 2028-03-31 | 2028-06-30 | 2028-09-30 | 2028-12-31 | 2029-03-31 | 2029-06-30 | 2029-09-30 | 2029-12-31 | 2030-03-31 | 2030-06-30 | 2030-09-30 | 2030-12-31 | 2031-03-31 | 2031-06-30 | 2031-09-30 | 2031-12-31 | 2032-03-31 | 2032-06-30 | 2032-09-30 | 2032-12-31 | 2033-03-31 | 2033-06-30 | 2033-09-30 | 2033-12-31 | 2034-03-31 | 2034-06-30 | 2034-09-30 | 2034-12-31 | 2035-03-31 | 2035-06-30 | 2035-09-30 | 2035-12-31 | 2036-03-31 | 2036-06-30 | 2036-09-30 | 2036-12-31 | 2037-03-31
A. CURVE GALLERY – the five shapes over a 12-quarter window (for explanation & charts)
Window length used for the gallery (n) | 12
Position in window (i) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Upfront | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Even | 100% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333%
Front-loaded | 100% | 15.38% | 14.1% | 12.82% | 11.54% | 10.26% | 8.974% | 7.692% | 6.41% | 5.128% | 3.846% | 2.564% | 1.282%
Back-loaded | 100% | 1.282% | 2.564% | 3.846% | 5.128% | 6.41% | 7.692% | 8.974% | 10.26% | 11.54% | 12.82% | 14.1% | 15.38%
S-curve | 100% | 1.704% | 4.995% | 7.946% | 10.36% | 12.06% | 12.94% | 12.94% | 12.06% | 10.36% | 7.946% | 4.995% | 1.704%
S-curve – cumulative (the 'S' shape) |  | 1.704% | 6.699% | 14.64% | 25% | 37.06% | 50% | 62.94% | 75% | 85.36% | 93.3% | 98.3% | 100%
Formulas: Even = 1/n ¦ Front-loaded = 2(n−i+1)/[n(n+1)] ¦ Back-loaded = 2i/[n(n+1)] ¦ S-curve = sin(π(i−0.5)/n) × sin(π/2n) – this exact scaling makes the S-curve total 100%.
B. PRODUCT PHASING – share of each product's sales and construction in each quarter
Villas
Sales % (curve: as per INPUTS) | 100% | 0% | 0% | 22.22% | 19.44% | 16.67% | 13.89% | 11.11% | 8.333% | 5.556% | 2.778% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Sales % – cumulative |  | 0% | 0% | 22.22% | 41.67% | 58.33% | 72.22% | 83.33% | 91.67% | 97.22% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Construction % (curve: as per INPUTS) | 100% | 0% | 0% | 0% | 1.704% | 4.995% | 7.946% | 10.36% | 12.06% | 12.94% | 12.94% | 12.06% | 10.36% | 7.946% | 4.995% | 1.704% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Construction % – cumulative (drives CLP in Step 4) |  | 0% | 0% | 0% | 1.704% | 6.699% | 14.64% | 25% | 37.06% | 50% | 62.94% | 75% | 85.36% | 93.3% | 98.3% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Check (each must total 100%) | OK
Apartments – Towers A & B
Sales % (curve: as per INPUTS) | 100% | 0% | 0% | 0% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Sales % – cumulative |  | 0% | 0% | 0% | 8.333% | 16.67% | 25% | 33.33% | 41.67% | 50% | 58.33% | 66.67% | 75% | 83.33% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Construction % (curve: as per INPUTS) | 100% | 0% | 0% | 0% | 0% | 0.9607% | 2.845% | 4.62% | 6.218% | 7.577% | 8.644% | 9.38% | 9.755% | 9.755% | 9.38% | 8.644% | 7.577% | 6.218% | 4.62% | 2.845% | 0.9607% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Construction % – cumulative (drives CLP in Step 4) |  | 0% | 0% | 0% | 0% | 0.9607% | 3.806% | 8.427% | 14.64% | 22.22% | 30.87% | 40.25% | 50% | 59.75% | 69.13% | 77.78% | 85.36% | 91.57% | 96.19% | 99.04% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Check (each must total 100%) | OK
Studios
Sales % (curve: as per INPUTS) | 100% | 0% | 0% | 0% | 0% | 0% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 12.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Sales % – cumulative |  | 0% | 0% | 0% | 0% | 0% | 12.5% | 25% | 37.5% | 50% | 62.5% | 75% | 87.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Construction % (curve: as per INPUTS) | 100% | 0% | 0% | 0% | 0% | 0% | 1.704% | 4.995% | 7.946% | 10.36% | 12.06% | 12.94% | 12.94% | 12.06% | 10.36% | 7.946% | 4.995% | 1.704% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Construction % – cumulative (drives CLP in Step 4) |  | 0% | 0% | 0% | 0% | 0% | 1.704% | 6.699% | 14.64% | 25% | 37.06% | 50% | 62.94% | 75% | 85.36% | 93.3% | 98.3% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Check (each must total 100%) | OK
High-street retail
Sales % (curve: as per INPUTS) | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.778% | 5.556% | 8.333% | 11.11% | 13.89% | 16.67% | 19.44% | 22.22% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Sales % – cumulative |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.778% | 8.333% | 16.67% | 27.78% | 41.67% | 58.33% | 77.78% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Construction % (curve: as per INPUTS) | 100% | 0% | 0% | 0% | 0% | 0% | 1.704% | 4.995% | 7.946% | 10.36% | 12.06% | 12.94% | 12.94% | 12.06% | 10.36% | 7.946% | 4.995% | 1.704% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Construction % – cumulative (drives CLP in Step 4) |  | 0% | 0% | 0% | 0% | 0% | 1.704% | 6.699% | 14.64% | 25% | 37.06% | 50% | 62.94% | 75% | 85.36% | 93.3% | 98.3% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Check (each must total 100%) | OK
Product row 5 (off)
Sales % (curve: as per INPUTS) | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Sales % – cumulative | [13 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Construction % (curve: as per INPUTS) | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Construction % – cumulative (drives CLP in Step 4) | [13 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Check (each must total 100%) | Off
Product row 6 (off)
Sales % (curve: as per INPUTS) | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Sales % – cumulative | [13 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Construction % (curve: as per INPUTS) | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Construction % – cumulative (drives CLP in Step 4) | [13 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Check (each must total 100%) | Off
Product row 7 (off)
Sales % (curve: as per INPUTS) | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Sales % – cumulative | [13 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Construction % (curve: as per INPUTS) | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Construction % – cumulative (drives CLP in Step 4) | [13 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Check (each must total 100%) | Off
Product row 8 (off)
Sales % (curve: as per INPUTS) | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Sales % – cumulative | [13 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Construction % (curve: as per INPUTS) | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Construction % – cumulative (drives CLP in Step 4) | [13 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Check (each must total 100%) | Off
Product row 9 (off)
Sales % (curve: as per INPUTS) | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Sales % – cumulative | [13 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Construction % (curve: as per INPUTS) | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Construction % – cumulative (drives CLP in Step 4) | [13 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Check (each must total 100%) | Off
Product row 10 (off)
Sales % (curve: as per INPUTS) | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Sales % – cumulative | [13 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Construction % (curve: as per INPUTS) | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Construction % – cumulative (drives CLP in Step 4) | [13 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Check (each must total 100%) | Off
C. AGGREGATE PROFILES – used by cost heads set to 'Follow Sales' / 'Follow Construction'
Sales profile (share of total sales value booked) | 100% | 0% | 0% | 7.61% | 11.33% | 10.38% | 9.987% | 9.036% | 8.23% | 7.424% | 6.618% | 5.812% | 5.957% | 6.102% | 5.687% | 5.832% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Construction profile – all products (share of construction cost) | 100% | 0% | 0% | 0% | 0.4568% | 1.957% | 4.112% | 6.191% | 7.937% | 9.261% | 10.1% | 10.41% | 10.2% | 9.473% | 8.29% | 6.722% | 5.317% | 4.152% | 2.973% | 1.831% | 0.6182% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Construction profile – Villa products | 100% | 0% | 0% | 0% | 1.704% | 4.995% | 7.946% | 10.36% | 12.06% | 12.94% | 12.94% | 12.06% | 10.36% | 7.946% | 4.995% | 1.704% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Construction profile – Apartment products | 100% | 0% | 0% | 0% | 0% | 0.9607% | 2.845% | 4.62% | 6.218% | 7.577% | 8.644% | 9.38% | 9.755% | 9.755% | 9.38% | 8.644% | 7.577% | 6.218% | 4.62% | 2.845% | 0.9607% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Construction profile – Studio products | 100% | 0% | 0% | 0% | 0% | 0% | 1.704% | 4.995% | 7.946% | 10.36% | 12.06% | 12.94% | 12.94% | 12.06% | 10.36% | 7.946% | 4.995% | 1.704% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Construction profile – Plot products | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Construction profile – Institutional products | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Construction profile – Commercial products | 100% | 0% | 0% | 0% | 0% | 0% | 1.704% | 4.995% | 7.946% | 10.36% | 12.06% | 12.94% | 12.94% | 12.06% | 10.36% | 7.946% | 4.995% | 1.704% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Construction profile – EWS/LIG products | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Collections profile (share of total collections – from COLLECTIONS) | 100% | 0% | 0% | 0.761% | 1.894% | 3.598% | 2.607% | 4.851% | 8.748% | 5.692% | 8.538% | 11.81% | 6.945% | 4.199% | 10.77% | 7.848% | 9.56% | 3.773% | 2.802% | 0% | 5.604% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Collections come from the COLLECTIONS sheet (Step 4). Heads set to 'Follow Collections' (e.g. the JV landowner share) use this row.
D. COST HEAD PHASING – share of each cost head spent in each quarter
Land Cost | Follow Collections
Spend % | 100% | 0% | 0% | 0.761% | 1.894% | 3.598% | 2.607% | 4.851% | 8.748% | 5.692% | 8.538% | 11.81% | 6.945% | 4.199% | 10.77% | 7.848% | 9.56% | 3.773% | 2.802% | 0% | 5.604% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Check | OK
Stamp Duty | Upfront
Spend % | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Check | OK
Brokerage | Upfront
Spend % | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Check | OK
Villa Construction Cost | Follow Construction
Spend % | 100% | 0% | 0% | 0% | 1.704% | 4.995% | 7.946% | 10.36% | 12.06% | 12.94% | 12.94% | 12.06% | 10.36% | 7.946% | 4.995% | 1.704% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Check | OK
APT Construction Cost | Follow Construction
Spend % | 100% | 0% | 0% | 0% | 0% | 0.9607% | 2.845% | 4.62% | 6.218% | 7.577% | 8.644% | 9.38% | 9.755% | 9.755% | 9.38% | 8.644% | 7.577% | 6.218% | 4.62% | 2.845% | 0.9607% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Check | OK
Studio Construction cost with furnishing | Follow Construction
Spend % | 100% | 0% | 0% | 0% | 0% | 0% | 1.704% | 4.995% | 7.946% | 10.36% | 12.06% | 12.94% | 12.94% | 12.06% | 10.36% | 7.946% | 4.995% | 1.704% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Check | OK
Plotted Construction Development Cost | Follow Construction
Spend % | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Check | Zero
Institutional Plotted Development Cost | Follow Construction
Spend % | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Check | Zero
Commercial Construction Cost | Follow Construction
Spend % | 100% | 0% | 0% | 0% | 0% | 0% | 1.704% | 4.995% | 7.946% | 10.36% | 12.06% | 12.94% | 12.94% | 12.06% | 10.36% | 7.946% | 4.995% | 1.704% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Check | OK
EWS/LIG plots development cost | Follow Construction
Spend % | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Check | Zero
Corporate Overheads (₹/Sq Ft SA) | Follow Project Life
Spend % | 100% | [12 empty] | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Check | OK
Marketing & Sales @ % | Follow Sales
Spend % | 100% | 0% | 0% | 7.61% | 11.33% | 10.38% | 9.987% | 9.036% | 8.23% | 7.424% | 6.618% | 5.812% | 5.957% | 6.102% | 5.687% | 5.832% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Check | OK
Legal & Compliance (₹/Sq Ft SA) | Front-loaded
Spend % | 100% | 22.22% | 19.44% | 16.67% | 13.89% | 11.11% | 8.333% | 5.556% | 2.778% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Check | OK
EWS / LIG @ ₹/Sq Ft (Builtup) | Follow Construction
Spend % | 100% | 0% | 0% | 0% | 0.4568% | 1.957% | 4.112% | 6.191% | 7.937% | 9.261% | 10.1% | 10.41% | 10.2% | 9.473% | 8.29% | 6.722% | 5.317% | 4.152% | 2.973% | 1.831% | 0.6182% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Check | OK
Contingency @ % | Follow Construction
Spend % | 100% | 0% | 0% | 0% | 0.4568% | 1.957% | 4.112% | 6.191% | 7.937% | 9.261% | 10.1% | 10.41% | 10.2% | 9.473% | 8.29% | 6.722% | 5.317% | 4.152% | 2.973% | 1.831% | 0.6182% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Check | OK
External Development & Landscaping | Follow Construction
Spend % | 100% | 0% | 0% | 0% | 0.4568% | 1.957% | 4.112% | 6.191% | 7.937% | 9.261% | 10.1% | 10.41% | 10.2% | 9.473% | 8.29% | 6.722% | 5.317% | 4.152% | 2.973% | 1.831% | 0.6182% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Check | OK
Hotel Brand Key fee ₹50K per Key for smaller brand | Follow Construction
Spend % | 100% | 0% | 0% | 0% | 0.4568% | 1.957% | 4.112% | 6.191% | 7.937% | 9.261% | 10.1% | 10.41% | 10.2% | 9.473% | 8.29% | 6.722% | 5.317% | 4.152% | 2.973% | 1.831% | 0.6182% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Check | OK
Furnishing Cost for Studios | Follow Construction
Spend % | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Check | Off
GST cost in case of commercial/Plotting development | At Project End
Spend % | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Check | Off
AIF Cost | Follow Project Life
Spend % | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Check | Off
BAR / Premium FAR Cost | Upfront
Spend % | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Check | OK
Spare cost row
Spend % | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Check
Spare cost row
Spend % | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Check
Spare cost row
Spend % | 0% | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | bar: 1 to 12
Check
E. CURVE CHECKS
Gallery: every curve totals 100% | OK
Every included product: sales & construction total 100% | OK
Sales profile totals 100% | OK
Collections profile totals 100% | OK
Construction profile totals 100% | OK
Category profiles total 100% (or 0% if no such product) | OK
Every applicable cost head totals 100% | OK

## COLLECTIONS
COLLECTIONS ENGINE — bookings → CLP milestones → cash actually received
Collections engine status | OK
No inputs here. Bookings = revenue × sales curve. Each milestone is collected when due: booking-linked milestones k quarters after booking; construction-linked milestones when cumulative construction reaches the trigger % (late buyers catch up after the lag). All ₹ Crore.
Quarter | Total | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 | Q17 | Q18 | Q19 | Q20 | Q21 | Q22 | Q23 | Q24 | Q25 | Q26 | Q27 | Q28 | Q29 | Q30 | Q31 | Q32 | Q33 | Q34 | Q35 | Q36 | Q37 | Q38 | Q39 | Q40
Quarter number (t) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Quarter end |  | 2027-06-30 | 2027-09-30 | 2027-12-31 | 2028-03-31 | 2028-06-30 | 2028-09-30 | 2028-12-31 | 2029-03-31 | 2029-06-30 | 2029-09-30 | 2029-12-31 | 2030-03-31 | 2030-06-30 | 2030-09-30 | 2030-12-31 | 2031-03-31 | 2031-06-30 | 2031-09-30 | 2031-12-31 | 2032-03-31 | 2032-06-30 | 2032-09-30 | 2032-12-31 | 2033-03-31 | 2033-06-30 | 2033-09-30 | 2033-12-31 | 2034-03-31 | 2034-06-30 | 2034-09-30 | 2034-12-31 | 2035-03-31 | 2035-06-30 | 2035-09-30 | 2035-12-31 | 2036-03-31 | 2036-06-30 | 2036-09-30 | 2036-12-31 | 2037-03-31
A. MILESTONE SCHEDULE – which quarter each CLP milestone falls due, per product
Trigger quarter for construction-linked milestones = first quarter in which that product's cumulative construction % reaches the trigger (from CURVES).
Product / milestone | Trigger type | 2027-06-30: Trigger value; 2027-09-30: % of sale; 2027-12-31: Due (construction-linked); 2028-03-31: Plain English
Villas → CLP – Villa
Earnest money | Booking + quarters | 2027-06-30: 0; 2027-09-30: 10%; 2028-03-31: at booking
Agreement to sell (ATS) | Booking + quarters | 2027-06-30: 1; 2027-09-30: 10%; 2028-03-31: 1 qtr(s) after booking
Commencement of construction | Construction % complete | 2027-06-30: 0.05; 2027-09-30: 10%; 2027-12-31: 5; 2028-03-31: construction 5% reached in Q5
Ground plinth | Construction % complete | 2027-06-30: 0.15; 2027-09-30: 10%; 2027-12-31: 7; 2028-03-31: construction 15% reached in Q7
First floor roof casting | Construction % complete | 2027-06-30: 0.35; 2027-09-30: 15%; 2027-12-31: 8; 2028-03-31: construction 35% reached in Q8
Second floor roof casting | Construction % complete | 2027-06-30: 0.55; 2027-09-30: 15%; 2027-12-31: 10; 2028-03-31: construction 55% reached in Q10
Third floor roof casting | Construction % complete | 2027-06-30: 0.75; 2027-09-30: 15%; 2027-12-31: 11; 2028-03-31: construction 75% reached in Q11
Completion certificate (CC) | Construction % complete | 2027-06-30: 0.95; 2027-09-30: 5%; 2027-12-31: 14; 2028-03-31: construction 95% reached in Q14
Possession | Construction % complete | 2027-06-30: 1; 2027-09-30: 10%; 2027-12-31: 15; 2028-03-31: construction 100% reached in Q15
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
Booking-linked % by lag (0 … 12 quarters after booking) → |  | 2027-06-30: 10%; 2027-09-30: 10%; 2027-12-31: 0%; 2028-03-31: 0%; 2028-06-30: 0%; 2028-09-30: 0%; 2028-12-31: 0%; 2029-03-31: 0%; 2029-06-30: 0%; 2029-09-30: 0%; 2029-12-31: 0%; 2030-03-31: 0%; 2030-06-30: 0%
Milestone check | OK
Apartments – Towers A & B → CLP – Apartment
Booking amount | Booking + quarters | 2027-06-30: 0; 2027-09-30: 10%; 2028-03-31: at booking
Agreement to sell (ATS) | Booking + quarters | 2027-06-30: 1; 2027-09-30: 10%; 2028-03-31: 1 qtr(s) after booking
Foundation completion | Construction % complete | 2027-06-30: 0.1; 2027-09-30: 10%; 2027-12-31: 8; 2028-03-31: construction 10% reached in Q8
Podium / plinth | Construction % complete | 2027-06-30: 0.2; 2027-09-30: 10%; 2027-12-31: 9; 2028-03-31: construction 20% reached in Q9
Slab casting – 25% floors | Construction % complete | 2027-06-30: 0.35; 2027-09-30: 10%; 2027-12-31: 11; 2028-03-31: construction 35% reached in Q11
Slab casting – 50% floors | Construction % complete | 2027-06-30: 0.5; 2027-09-30: 10%; 2027-12-31: 12; 2028-03-31: construction 50% reached in Q12
Slab casting – 75% floors | Construction % complete | 2027-06-30: 0.65; 2027-09-30: 10%; 2027-12-31: 14; 2028-03-31: construction 65% reached in Q14
Top slab casting | Construction % complete | 2027-06-30: 0.8; 2027-09-30: 10%; 2027-12-31: 16; 2028-03-31: construction 80% reached in Q16
Brickwork & plaster | Construction % complete | 2027-06-30: 0.9; 2027-09-30: 5%; 2027-12-31: 17; 2028-03-31: construction 90% reached in Q17
Flooring & finishing | Construction % complete | 2027-06-30: 0.95; 2027-09-30: 5%; 2027-12-31: 18; 2028-03-31: construction 95% reached in Q18
Possession | Construction % complete | 2027-06-30: 1; 2027-09-30: 10%; 2027-12-31: 20; 2028-03-31: construction 100% reached in Q20
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
Booking-linked % by lag (0 … 12 quarters after booking) → |  | 2027-06-30: 10%; 2027-09-30: 10%; 2027-12-31: 0%; 2028-03-31: 0%; 2028-06-30: 0%; 2028-09-30: 0%; 2028-12-31: 0%; 2029-03-31: 0%; 2029-06-30: 0%; 2029-09-30: 0%; 2029-12-31: 0%; 2030-03-31: 0%; 2030-06-30: 0%
Milestone check | OK
Studios → CLP – Apartment
Booking amount | Booking + quarters | 2027-06-30: 0; 2027-09-30: 10%; 2028-03-31: at booking
Agreement to sell (ATS) | Booking + quarters | 2027-06-30: 1; 2027-09-30: 10%; 2028-03-31: 1 qtr(s) after booking
Foundation completion | Construction % complete | 2027-06-30: 0.1; 2027-09-30: 10%; 2027-12-31: 8; 2028-03-31: construction 10% reached in Q8
Podium / plinth | Construction % complete | 2027-06-30: 0.2; 2027-09-30: 10%; 2027-12-31: 9; 2028-03-31: construction 20% reached in Q9
Slab casting – 25% floors | Construction % complete | 2027-06-30: 0.35; 2027-09-30: 10%; 2027-12-31: 10; 2028-03-31: construction 35% reached in Q10
Slab casting – 50% floors | Construction % complete | 2027-06-30: 0.5; 2027-09-30: 10%; 2027-12-31: 11; 2028-03-31: construction 50% reached in Q11
Slab casting – 75% floors | Construction % complete | 2027-06-30: 0.65; 2027-09-30: 10%; 2027-12-31: 13; 2028-03-31: construction 65% reached in Q13
Top slab casting | Construction % complete | 2027-06-30: 0.8; 2027-09-30: 10%; 2027-12-31: 14; 2028-03-31: construction 80% reached in Q14
Brickwork & plaster | Construction % complete | 2027-06-30: 0.9; 2027-09-30: 5%; 2027-12-31: 15; 2028-03-31: construction 90% reached in Q15
Flooring & finishing | Construction % complete | 2027-06-30: 0.95; 2027-09-30: 5%; 2027-12-31: 16; 2028-03-31: construction 95% reached in Q16
Possession | Construction % complete | 2027-06-30: 1; 2027-09-30: 10%; 2027-12-31: 17; 2028-03-31: construction 100% reached in Q17
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
Booking-linked % by lag (0 … 12 quarters after booking) → |  | 2027-06-30: 10%; 2027-09-30: 10%; 2027-12-31: 0%; 2028-03-31: 0%; 2028-06-30: 0%; 2028-09-30: 0%; 2028-12-31: 0%; 2029-03-31: 0%; 2029-06-30: 0%; 2029-09-30: 0%; 2029-12-31: 0%; 2030-03-31: 0%; 2030-06-30: 0%
Milestone check | OK
High-street retail → Down Payment Plan
Booking amount | Booking + quarters | 2027-06-30: 0; 2027-09-30: 10%; 2028-03-31: at booking
Down payment | Booking + quarters | 2027-06-30: 1; 2027-09-30: 80%; 2028-03-31: 1 qtr(s) after booking
Possession | Construction % complete | 2027-06-30: 1; 2027-09-30: 10%; 2027-12-31: 17; 2028-03-31: construction 100% reached in Q17
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
Booking-linked % by lag (0 … 12 quarters after booking) → |  | 2027-06-30: 10%; 2027-09-30: 80%; 2027-12-31: 0%; 2028-03-31: 0%; 2028-06-30: 0%; 2028-09-30: 0%; 2028-12-31: 0%; 2029-03-31: 0%; 2029-06-30: 0%; 2029-09-30: 0%; 2029-12-31: 0%; 2030-03-31: 0%; 2030-06-30: 0%
Milestone check | OK
Product row 5 (off)
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
Booking-linked % by lag (0 … 12 quarters after booking) → | bar: 2027-06-30 to 2030-06-30
Milestone check | Off
Product row 6 (off)
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
Booking-linked % by lag (0 … 12 quarters after booking) → | bar: 2027-06-30 to 2030-06-30
Milestone check | Off
Product row 7 (off)
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
Booking-linked % by lag (0 … 12 quarters after booking) → | bar: 2027-06-30 to 2030-06-30
Milestone check | Off
Product row 8 (off)
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
Booking-linked % by lag (0 … 12 quarters after booking) → | bar: 2027-06-30 to 2030-06-30
Milestone check | Off
Product row 9 (off)
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
Booking-linked % by lag (0 … 12 quarters after booking) → | bar: 2027-06-30 to 2030-06-30
Milestone check | Off
Product row 10 (off)
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
Booking-linked % by lag (0 … 12 quarters after booking) → | bar: 2027-06-30 to 2030-06-30
Milestone check | Off
B. PRODUCT CASH – bookings, collections (booking-linked + construction-linked), receivables (₹ Crore)
Construction-linked: in a milestone's trigger quarter, all buyers so far (after the catch-up lag) pay it; afterwards each new buyer pays it as catch-up. Works for any number of milestones.
Villas
Bookings (sales value booked) | 275 | 0 | 0 | 61.1111 | 53.4722 | 45.8333 | 38.1944 | 30.5556 | 22.9167 | 15.2778 | 7.6389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bookings – cumulative |  | 0 | 0 | 61.1111 | 114.5833 | 160.4167 | 198.6111 | 229.1667 | 252.0833 | 267.3611 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275
Booking-linked milestones (booking, ATS, down payment …) | 55 | 0 | 0 | 6.1111 | 11.4583 | 9.9306 | 8.4028 | 6.875 | 5.3472 | 3.8194 | 2.2917 | 0.76389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction-linked milestones (incl. catch-up) | 220 | 0 | 0 | 0 | 0 | 11.4583 | 4.5833 | 23.6806 | 40.4861 | 8.0208 | 45.4514 | 45.0694 | 0 | 0 | 13.75 | 27.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections (cash received) | 275 | 0 | 0 | 6.1111 | 11.4583 | 21.3889 | 12.9861 | 30.5556 | 45.8333 | 11.8403 | 47.7431 | 45.8333 | 0 | 0 | 13.75 | 27.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections – cumulative |  | 0 | 0 | 6.1111 | 17.5694 | 38.9583 | 51.9444 | 82.5 | 128.3333 | 140.1736 | 187.9167 | 233.75 | 233.75 | 233.75 | 247.5 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275 | 275
Receivables (booked, not yet collected) |  | 0 | 0 | 55 | 97.0139 | 121.4583 | 146.6667 | 146.6667 | 123.75 | 127.1875 | 87.0833 | 41.25 | 41.25 | 41.25 | 27.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% of revenue collected – cumulative |  | 0% | 0% | 2.222% | 6.389% | 14.17% | 18.89% | 30% | 46.67% | 50.97% | 68.33% | 85% | 85% | 85% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Check | OK
Apartments – Towers A & B
Bookings (sales value booked) | 450 | 0 | 0 | 0 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bookings – cumulative |  | 0 | 0 | 0 | 37.5 | 75 | 112.5 | 150 | 187.5 | 225 | 262.5 | 300 | 337.5 | 375 | 412.5 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450
Booking-linked milestones (booking, ATS, down payment …) | 90 | 0 | 0 | 0 | 3.75 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction-linked milestones (incl. catch-up) | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 22.5 | 7.5 | 33.75 | 41.25 | 15 | 52.5 | 18.75 | 63.75 | 22.5 | 22.5 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections (cash received) | 450 | 0 | 0 | 0 | 3.75 | 7.5 | 7.5 | 7.5 | 22.5 | 30 | 15 | 41.25 | 48.75 | 22.5 | 60 | 26.25 | 67.5 | 22.5 | 22.5 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections – cumulative |  | 0 | 0 | 0 | 3.75 | 11.25 | 18.75 | 26.25 | 48.75 | 78.75 | 93.75 | 135 | 183.75 | 206.25 | 266.25 | 292.5 | 360 | 382.5 | 405 | 405 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450 | 450
Receivables (booked, not yet collected) |  | 0 | 0 | 0 | 33.75 | 63.75 | 93.75 | 123.75 | 138.75 | 146.25 | 168.75 | 165 | 153.75 | 168.75 | 146.25 | 157.5 | 90 | 67.5 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% of revenue collected – cumulative |  | 0% | 0% | 0% | 0.8333% | 2.5% | 4.167% | 5.833% | 10.83% | 17.5% | 20.83% | 30% | 40.83% | 45.83% | 59.17% | 65% | 80% | 85% | 90% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Check | OK
Studios
Bookings (sales value booked) | 36 | 0 | 0 | 0 | 0 | 0 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bookings – cumulative |  | 0 | 0 | 0 | 0 | 0 | 4.5 | 9 | 13.5 | 18 | 22.5 | 27 | 31.5 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Booking-linked milestones (booking, ATS, down payment …) | 7.2 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction-linked milestones (incl. catch-up) | 28.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 1.8 | 2.7 | 3.6 | 1.8 | 4.95 | 5.85 | 1.8 | 1.8 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections (cash received) | 36 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0.9 | 1.8 | 2.7 | 3.6 | 4.5 | 2.7 | 5.85 | 6.3 | 1.8 | 1.8 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections – cumulative |  | 0 | 0 | 0 | 0 | 0 | 0.45 | 1.35 | 3.15 | 5.85 | 9.45 | 13.95 | 16.65 | 22.5 | 28.8 | 30.6 | 32.4 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Receivables (booked, not yet collected) |  | 0 | 0 | 0 | 0 | 0 | 4.05 | 7.65 | 10.35 | 12.15 | 13.05 | 13.05 | 14.85 | 13.5 | 7.2 | 5.4 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% of revenue collected – cumulative |  | 0% | 0% | 0% | 0% | 0% | 1.25% | 3.75% | 8.75% | 16.25% | 26.25% | 38.75% | 46.25% | 62.5% | 80% | 85% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Check | OK
High-street retail
Bookings (sales value booked) | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1667 | 2.3333 | 3.5 | 4.6667 | 5.8333 | 7 | 8.1667 | 9.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bookings – cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1667 | 3.5 | 7 | 11.6667 | 17.5 | 24.5 | 32.6667 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
Booking-linked milestones (booking, ATS, down payment …) | 37.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11667 | 1.1667 | 2.2167 | 3.2667 | 4.3167 | 5.3667 | 6.4167 | 7.4667 | 7.4667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction-linked milestones (incl. catch-up) | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections (cash received) | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11667 | 1.1667 | 2.2167 | 3.2667 | 4.3167 | 5.3667 | 6.4167 | 7.4667 | 7.4667 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections – cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11667 | 1.2833 | 3.5 | 6.7667 | 11.0833 | 16.45 | 22.8667 | 30.3333 | 37.8 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42 | 42
Receivables (booked, not yet collected) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.05 | 2.2167 | 3.5 | 4.9 | 6.4167 | 8.05 | 9.8 | 11.6667 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% of revenue collected – cumulative |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2778% | 3.056% | 8.333% | 16.11% | 26.39% | 39.17% | 54.44% | 72.22% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Check | OK
Product row 5 (off)
Bookings (sales value booked) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bookings – cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Booking-linked milestones (booking, ATS, down payment …) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction-linked milestones (incl. catch-up) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections (cash received) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections – cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Receivables (booked, not yet collected) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% of revenue collected – cumulative | bar: 2027-06-30 to 2037-03-31
Check | Off
Product row 6 (off)
Bookings (sales value booked) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bookings – cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Booking-linked milestones (booking, ATS, down payment …) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction-linked milestones (incl. catch-up) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections (cash received) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections – cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Receivables (booked, not yet collected) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% of revenue collected – cumulative | bar: 2027-06-30 to 2037-03-31
Check | Off
Product row 7 (off)
Bookings (sales value booked) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bookings – cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Booking-linked milestones (booking, ATS, down payment …) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction-linked milestones (incl. catch-up) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections (cash received) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections – cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Receivables (booked, not yet collected) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% of revenue collected – cumulative | bar: 2027-06-30 to 2037-03-31
Check | Off
Product row 8 (off)
Bookings (sales value booked) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bookings – cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Booking-linked milestones (booking, ATS, down payment …) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction-linked milestones (incl. catch-up) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections (cash received) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections – cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Receivables (booked, not yet collected) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% of revenue collected – cumulative | bar: 2027-06-30 to 2037-03-31
Check | Off
Product row 9 (off)
Bookings (sales value booked) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bookings – cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Booking-linked milestones (booking, ATS, down payment …) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction-linked milestones (incl. catch-up) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections (cash received) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections – cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Receivables (booked, not yet collected) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% of revenue collected – cumulative | bar: 2027-06-30 to 2037-03-31
Check | Off
Product row 10 (off)
Bookings (sales value booked) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bookings – cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Booking-linked milestones (booking, ATS, down payment …) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction-linked milestones (incl. catch-up) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections (cash received) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections – cumulative |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Receivables (booked, not yet collected) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% of revenue collected – cumulative | bar: 2027-06-30 to 2037-03-31
Check | Off
C. PROJECT TOTALS & SPLIT (₹ Crore)
Total bookings | 803 | 0 | 0 | 61.1111 | 90.9722 | 83.3333 | 80.1944 | 72.5556 | 66.0833 | 59.6111 | 53.1389 | 46.6667 | 47.8333 | 49 | 45.6667 | 46.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total collections (cash inflow) | 803 | 0 | 0 | 6.1111 | 15.2083 | 28.8889 | 20.9361 | 38.9556 | 70.25 | 45.7069 | 68.5597 | 94.85 | 55.7667 | 33.7167 | 86.4667 | 63.0167 | 76.7667 | 30.3 | 22.5 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total collections – cumulative |  | 0 | 0 | 6.1111 | 21.3194 | 50.2083 | 71.1444 | 110.1 | 180.35 | 226.0569 | 294.6167 | 389.4667 | 445.2333 | 478.95 | 565.4167 | 628.4333 | 705.2 | 735.5 | 758 | 758 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803
Total receivables |  | 0 | 0 | 55 | 130.7639 | 185.2083 | 244.4667 | 278.0667 | 273.9 | 287.8042 | 272.3833 | 224.2 | 216.2667 | 231.55 | 190.75 | 174.5667 | 97.8 | 67.5 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Landowner share of collections (JV) | 256.96 | 0 | 0 | 1.9556 | 4.8667 | 9.2444 | 6.6996 | 12.4658 | 22.48 | 14.6262 | 21.9391 | 30.352 | 17.8453 | 10.7893 | 27.6693 | 20.1653 | 24.5653 | 9.696 | 7.2 | 0 | 14.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Developer share of collections | 546.04 | 0 | 0 | 4.1556 | 10.3417 | 19.6444 | 14.2366 | 26.4898 | 47.77 | 31.0807 | 46.6206 | 64.498 | 37.9213 | 22.9273 | 58.7973 | 42.8513 | 52.2013 | 20.604 | 15.3 | 0 | 30.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collections profile (% of total collections) | 100% | 0% | 0% | 0.761% | 1.894% | 3.598% | 2.607% | 4.851% | 8.748% | 5.692% | 8.538% | 11.81% | 6.945% | 4.199% | 10.77% | 7.848% | 9.56% | 3.773% | 2.802% | 0% | 5.604% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Collections are shown excluding GST. The landowner share equals the JV land cost head phased by 'Follow Collections'.
D. COLLECTION CHECKS
Every included product: bookings = collections = revenue | OK
Total collections = total revenue (nothing lost beyond the horizon) | OK
Receivables never negative (no cash before a sale) | OK
Receivables fully cleared by the last quarter | OK
Every construction milestone is reached inside the model | OK
Every active product's payment plan totals 100% | OK
LO share + developer share = total collections | OK

## CASHFLOW
CASH FLOW & RETURNS — inflows, outflows, landowner payments, IRR, NPV, peak investment, break-even
Cash flow engine status | OK
No inputs here. Outflow of each cost head = amount × its phasing % (CURVES). In a JV, items in the initial-investment table are paid early at their payout quarter and only the balance follows the curve – so nothing is counted twice. All ₹ Crore.
Quarter | Total | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 | Q17 | Q18 | Q19 | Q20 | Q21 | Q22 | Q23 | Q24 | Q25 | Q26 | Q27 | Q28 | Q29 | Q30 | Q31 | Q32 | Q33 | Q34 | Q35 | Q36 | Q37 | Q38 | Q39 | Q40
Quarter number (t) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Quarter end |  | 2027-06-30 | 2027-09-30 | 2027-12-31 | 2028-03-31 | 2028-06-30 | 2028-09-30 | 2028-12-31 | 2029-03-31 | 2029-06-30 | 2029-09-30 | 2029-12-31 | 2030-03-31 | 2030-06-30 | 2030-09-30 | 2030-12-31 | 2031-03-31 | 2031-06-30 | 2031-09-30 | 2031-12-31 | 2032-03-31 | 2032-06-30 | 2032-09-30 | 2032-12-31 | 2033-03-31 | 2033-06-30 | 2033-09-30 | 2033-12-31 | 2034-03-31 | 2034-06-30 | 2034-09-30 | 2034-12-31 | 2035-03-31 | 2035-06-30 | 2035-09-30 | 2035-12-31 | 2036-03-31 | 2036-06-30 | 2036-09-30 | 2036-12-31 | 2037-03-31
A. CASH INFLOWS
Customer collections (100%) | 803 | 0 | 0 | 6.1111 | 15.2083 | 28.8889 | 20.9361 | 38.9556 | 70.25 | 45.7069 | 68.5597 | 94.85 | 55.7667 | 33.7167 | 86.4667 | 63.0167 | 76.7667 | 30.3 | 22.5 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
of which landowner share earned (JV) | 256.96 | 0 | 0 | 1.9556 | 4.8667 | 9.2444 | 6.6996 | 12.4658 | 22.48 | 14.6262 | 21.9391 | 30.352 | 17.8453 | 10.7893 | 27.6693 | 20.1653 | 24.5653 | 9.696 | 7.2 | 0 | 14.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
of which developer share | 546.04 | 0 | 0 | 4.1556 | 10.3417 | 19.6444 | 14.2366 | 26.4898 | 47.77 | 31.0807 | 46.6206 | 64.498 | 37.9213 | 22.9273 | 58.7973 | 42.8513 | 52.2013 | 20.604 | 15.3 | 0 | 30.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B. CASH OUTFLOWS BY COST HEAD (landowner share shown separately in Section C)
Total
Land cost – JV: paid as landowner share (Section C) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Stamp Duty | 0.89675 | 0 | 0.89675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brokerage | 2.124 | 0 | 2.124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Villa Construction Cost | 72.5 | 0 | 0 | 0 | 1.2352 | 3.6214 | 5.7608 | 7.5076 | 8.7428 | 9.3822 | 9.3822 | 8.7428 | 7.5076 | 5.7608 | 3.6214 | 1.2352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
APT Construction Cost | 174 | 0 | 0 | 0 | 0 | 1.6717 | 4.9508 | 8.0397 | 10.8196 | 13.1837 | 15.0412 | 16.3206 | 16.9729 | 16.9729 | 16.3206 | 15.0412 | 13.1837 | 10.8196 | 8.0397 | 4.9508 | 1.6717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Studio Construction cost with furnishing | 15.2 | 0 | 0 | 0 | 0 | 0 | 0.25896 | 0.75924 | 1.2078 | 1.574 | 1.833 | 1.967 | 1.967 | 1.833 | 1.574 | 1.2078 | 0.75924 | 0.25896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Plotted Construction Development Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Institutional Plotted Development Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Commercial Construction Cost | 8.7 | 0 | 0 | 0 | 0 | 0 | 0.14822 | 0.43457 | 0.6913 | 0.90091 | 1.0491 | 1.1259 | 1.1259 | 1.0491 | 0.90091 | 0.6913 | 0.43457 | 0.14822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EWS/LIG plots development cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Corporate Overheads (₹/Sq Ft SA) | 32.12 | 1.606 | 1.606 | 1.606 | 1.606 | 1.606 | 1.606 | 1.606 | 1.606 | 1.606 | 1.606 | 1.606 | 1.606 | 1.606 | 1.606 | 1.606 | 1.606 | 1.606 | 1.606 | 1.606 | 1.606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marketing & Sales @ % | 56.21 | 0 | 0 | 4.2778 | 6.3681 | 5.8333 | 5.6136 | 5.0789 | 4.6258 | 4.1728 | 3.7197 | 3.2667 | 3.3483 | 3.43 | 3.1967 | 3.2783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legal & Compliance (₹/Sq Ft SA) | 6.9 | 0 | 6.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EWS / LIG @ ₹/Sq Ft (Builtup) | 1.84 | 0 | 0 | 0 | 0.0084051 | 0.036018 | 0.07566 | 0.11392 | 0.14604 | 0.1704 | 0.18581 | 0.1916 | 0.18763 | 0.17431 | 0.15254 | 0.12368 | 0.097835 | 0.076395 | 0.054708 | 0.033689 | 0.011375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingency @ % | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
External Development & Landscaping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hotel Brand Key fee ₹50K per Key for smaller brand | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Furnishing Cost for Studios | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
GST cost in case of commercial/Plotting development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AIF Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BAR / Premium FAR Cost | 3.1546 | 0 | 3.1546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Spare cost row | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Spare cost row | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Spare cost row | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total outflows (excl. landowner share) | 373.6453 | 1.606 | 14.6813 | 5.8838 | 9.2176 | 12.7684 | 18.4141 | 23.5399 | 27.8393 | 30.99 | 32.817 | 33.2206 | 32.7153 | 30.8261 | 27.3721 | 23.1834 | 16.0813 | 12.9091 | 9.7004 | 6.5905 | 3.2891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. LANDOWNER PAYMENTS (JV) – advance paid early, then recovered from his share
Advance to landowner paid (token, DD, DA) | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advance – cumulative |  | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
Landowner share earned – cumulative |  | 0 | 0 | 1.9556 | 6.8222 | 16.0667 | 22.7662 | 35.232 | 57.712 | 72.3382 | 94.2773 | 124.6293 | 142.4747 | 153.264 | 180.9333 | 201.0987 | 225.664 | 235.36 | 242.56 | 242.56 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96
Paid to landowner – cumulative = greater of the two |  | 18 | 18 | 18 | 18 | 18 | 22.7662 | 35.232 | 57.712 | 72.3382 | 94.2773 | 124.6293 | 142.4747 | 153.264 | 180.9333 | 201.0987 | 225.664 | 235.36 | 242.56 | 242.56 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96 | 256.96
Cash paid to landowner this quarter | 256.96 | 18 | 0 | 0 | 0 | 0 | 4.7662 | 12.4658 | 22.48 | 14.6262 | 21.9391 | 30.352 | 17.8453 | 10.7893 | 27.6693 | 20.1653 | 24.5653 | 9.696 | 7.2 | 0 | 14.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Advance not yet recovered |  | 18 | 18 | 16.0444 | 11.1778 | 1.9333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Until his share of collections exceeds the advance, the landowner receives nothing more – that is how the advance is recovered.
D. NET CASH FLOWS
Project net cash flow (before landowner share in a JV) | 429.3547 | -1.606 | -14.6813 | 0.22733 | 5.9907 | 16.1205 | 2.5221 | 15.4157 | 42.4107 | 14.717 | 35.7427 | 61.6294 | 23.0513 | 2.8906 | 59.0945 | 39.8332 | 60.6853 | 17.3909 | 12.7996 | -6.5905 | 41.7109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project – cumulative |  | -1.606 | -16.2873 | -16.06 | -10.0693 | 6.0512 | 8.5732 | 23.9889 | 66.3995 | 81.1165 | 116.8593 | 178.4887 | 201.54 | 204.4306 | 263.5252 | 303.3584 | 364.0437 | 381.4346 | 394.2342 | 387.6437 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547 | 429.3547
Developer net cash flow (pre-tax) | 172.3947 | -19.606 | -14.6813 | 0.22733 | 5.9907 | 16.1205 | -2.2442 | 2.9499 | 19.9307 | 0.090752 | 13.8036 | 31.2774 | 5.206 | -7.8987 | 31.4252 | 19.6679 | 36.12 | 7.6949 | 5.5996 | -6.5905 | 27.3109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Developer – cumulative |  | -19.606 | -34.2873 | -34.06 | -28.0693 | -11.9488 | -14.193 | -11.2431 | 8.6875 | 8.7783 | 22.5819 | 53.8594 | 59.0654 | 51.1666 | 82.5918 | 102.2597 | 138.3797 | 146.0746 | 151.6742 | 145.0837 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947 | 172.3947
Tax (indicative – P&L tax spread in line with collections) | 44.8226 | 0 | 0 | 0.34112 | 0.84891 | 1.6125 | 1.1686 | 2.1745 | 3.9213 | 2.5513 | 3.8269 | 5.2944 | 3.1128 | 1.882 | 4.8265 | 3.5175 | 4.285 | 1.6913 | 1.2559 | 0 | 2.5119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Developer net cash flow (post-tax, indicative) | 127.5721 | -19.606 | -14.6813 | -0.11378 | 5.1418 | 14.5079 | -3.4128 | 0.77542 | 16.0094 | -2.4606 | 9.9767 | 25.983 | 2.0932 | -9.7808 | 26.5987 | 16.1504 | 31.835 | 6.0035 | 4.3437 | -6.5905 | 24.7991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Developer post-tax – cumulative |  | -19.606 | -34.2873 | -34.4011 | -29.2593 | -14.7514 | -18.1642 | -17.3888 | -1.3794 | -3.84 | 6.1367 | 32.1197 | 34.2129 | 24.4321 | 51.0309 | 67.1812 | 99.0162 | 105.0198 | 109.3635 | 102.773 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721 | 127.5721
helper: first positive quarter (project) |  | 999 | 999 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 999 | 20 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999
helper: first positive quarter (developer) |  | 999 | 999 | 3 | 4 | 5 | 999 | 7 | 8 | 9 | 10 | 11 | 12 | 999 | 14 | 15 | 16 | 17 | 18 | 999 | 20 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 999
helper: payback quarter (developer cumulative back to ≥ 0) |  | 999 | 999 | 999 | 999 | 999 | 999 | 999 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
E. RETURNS & FUNDING METRICS
Metric | Value | 999: Note
Project IRR – quarterly | 53.08% | 999: IRR of quarterly project cash flows
Project IRR – annualised | 449.1% | 999: (1 + quarterly IRR)^4 − 1
Developer IRR – quarterly | 20.41%
Developer IRR – annualised (pre-tax) | 110.2% | 999: Matches the 1244 definition (pre-tax)
Developer IRR – annualised (post-tax, indicative) | 83.89% | 999: Tax spread in line with collections – an approximation
Project NPV @ cost of equity (₹ Cr) | 251.6167 | 999: Discounted to the start of Q1 at the quarterly equivalent of the cost of equity
Developer NPV @ cost of equity (₹ Cr) | 90.6281
Peak investment – developer (₹ Cr) | 34.2873 | 999: Largest cumulative funding the developer must put in
Peak investment quarter | Q2
Peak investment date | 2027-09-30
Largest single-quarter deficit – developer (₹ Cr) | 19.606 | 999: The 1244 'peak investment' definition (one quarter, not cumulative)
Break-even quarter – project | Q3 | 999: First quarter with positive net cash flow (1244 definition)
Break-even date – project | 2027-12-31
Break-even quarter – developer | Q3
Break-even date – developer | 2027-12-31
Payback quarter – developer (cumulative cash back to zero) | Q8 | 999: Usually the more meaningful break-even
Payback date – developer | 2029-03-31
Cash multiple – developer (cash in ÷ cash out) | 4.3789 | 999: Cash-based cross-check of the equity multiple
F. YEARLY SUMMARY BY FINANCIAL YEAR (Apr–Mar)
Financial year | Total | 999: FY 2027-28; 999: FY 2028-29; 999: FY 2029-30; 999: FY 2030-31; 999: FY 2031-32; 999: FY 2032-33; 999: FY 2033-34; 8: FY 2034-35; 9: FY 2035-36; 10: FY 2036-37; 11: FY 2037-38
Collections | 803 | 999: 21.3194; 999: 159.0306; 999: 264.8833; 999: 259.9667; 999: 97.8; 999: 0; 999: 0; 8: 0; 9: 0; 10: 0; 11: 0
Outflows (excl. landowner) | 373.6453 | 999: 31.3887; 999: 82.5617; 999: 129.7428; 999: 97.463; 999: 32.4891; 999: 0; 999: 0; 8: 0; 9: 0; 10: 0; 11: 0
Paid to landowner | 256.96 | 999: 18; 999: 39.712; 999: 84.7627; 999: 83.1893; 999: 31.296; 999: 0; 999: 0; 8: 0; 9: 0; 10: 0; 11: 0
Developer net cash flow | 172.3947 | 999: -28.0693; 999: 36.7568; 999: 50.3778; 999: 79.3144; 999: 34.0149; 999: 0; 999: 0; 8: 0; 9: 0; 10: 0; 11: 0
Developer – cumulative |  | 999: -28.0693; 999: 8.6875; 999: 59.0654; 999: 138.3797; 999: 172.3947; 999: 172.3947; 999: 172.3947; 8: 172.3947; 9: 172.3947; 10: 172.3947; 11: 172.3947
G. CHART – developer cash flow
H. CASH FLOW CHECKS
Every cost head's outflows = its amount (landowner share separately) | OK
Early (initial-investment) amounts never exceed their cost head | OK
Early payout quarters inside the model | OK
Landowner paid exactly his share (advance fully recovered) | OK
Developer total cash = EBITDA (revenue − total cost) | OK
Project total cash = revenue − costs excl. landowner share | OK
Tax spread = P&L tax | OK
No cash flow outside the model horizon (all quarters ≤ horizon) | OK
I. CHART HELPER ROWS (used by the DASHBOARD)
Cumulative collections |  | 0 | 0 | 6.1111 | 21.3194 | 50.2083 | 71.1444 | 110.1 | 180.35 | 226.0569 | 294.6167 | 389.4667 | 445.2333 | 478.95 | 565.4167 | 628.4333 | 705.2 | 735.5 | 758 | 758 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803 | 803
Cumulative cash out (costs + landowner) |  | 19.606 | 34.2873 | 40.1711 | 49.3887 | 62.1572 | 85.3375 | 121.3431 | 171.6625 | 217.2786 | 272.0347 | 335.6073 | 386.168 | 427.7834 | 482.8248 | 526.1736 | 566.8203 | 589.4254 | 606.3258 | 612.9163 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053 | 630.6053

## OUTPUT
INVESTMENT FEASIBILITY REPORT ¦ OUTPUT DASHBOARD
Project Summary ¦ Revenue ¦ Cost ¦ P&L ¦ JV Split ¦ Key Metrics (all cash-flow metrics now live from the CASHFLOW sheet).
PROJECT SNAPSHOT
| Project | Location | Project type | Deal type | Land (acres) | Saleable area (sq ft)
| Project Aurora (Sample) | Sample City, Rajasthan | Mixed Development | JV | 6.1983 | 920000
A. REVENUE STATEMENT (₹ Crore)
| Revenue head (product) | ₹ Crore | ₹ / sq ft (saleable) | % of total revenue | Category
| Villas | 275 | 11000 | 34.25% | Villa
| Apartments – Towers A & B | 450 | 7500 | 56.04% | Apartment
| Studios | 36 | 9000 | 4.483% | Studio
| High-street retail | 42 | 14000 | 5.23% | Commercial
| — | 0 | 0 | 0%
| — | 0 | 0 | 0%
| — | 0 | 0 | 0%
| — | 0 | 0 | 0%
| — | 0 | 0 | 0%
| — | 0 | 0 | 0%
| TOTAL REVENUE excl. EWS / LIG | 803 | 8728.2609
| EWS / LIG sales revenue | 0
| SUM TOTAL REVENUE (A) | 803 | 8728.2609 | 100%
B. COST STATEMENT (₹ Crore)
| Cost head | ₹ Crore | ₹ / sq ft (saleable) | % of total revenue | Applicable?
| Land Cost | 256.96 | 2793.0435 | 32% | Yes
| Stamp Duty | 0.89675 | 9.7472 | 0.1117% | Yes
| Brokerage | 2.124 | 23.087 | 0.2645% | Yes
| Villa Construction Cost | 72.5 | 788.0435 | 9.029% | Yes
| APT Construction Cost | 174 | 1891.3043 | 21.67% | Yes
| Studio Construction cost with furnishing | 15.2 | 165.2174 | 1.893% | Yes
| Plotted Construction Development Cost | 0 | 0 | 0% | Yes
| Institutional Plotted Development Cost | 0 | 0 | 0% | Yes
| Commercial Construction Cost | 8.7 | 94.5652 | 1.083% | Yes
| EWS/LIG plots development cost | 0 | 0 | 0% | Yes
| Corporate Overheads (₹/Sq Ft SA) | 32.12 | 349.1304 | 4% | Yes
| Marketing & Sales @ % | 56.21 | 610.9783 | 7% | Yes
| Legal & Compliance (₹/Sq Ft SA) | 6.9 | 75 | 0.8593% | Yes
| EWS / LIG @ ₹/Sq Ft (Builtup) | 1.84 | 20 | 0.2291% | Yes
| Contingency @ % | 0 | 0 | 0% | Yes
| External Development & Landscaping | 0 | 0 | 0% | Yes
| Hotel Brand Key fee ₹50K per Key for smaller brand | 0 | 0 | 0% | Yes
| Furnishing Cost for Studios | 0 | 0 | 0% | No
| GST cost in case of commercial/Plotting development | 0 | 0 | 0% | No
| AIF Cost | 0 | 0 | 0% | No
| BAR / Premium FAR Cost | 3.1546 | 34.2889 | 0.3928% | Yes
| — | 0 | 0 | 0%
| — | 0 | 0 | 0%
| — | 0 | 0 | 0%
| TOTAL COST (B) | 630.6053 | 6854.4057 | 78.53%
| Total development cost (construction heads) | 270.4
C. PROFIT & LOSS STATEMENT (₹ Crore)
|  | ₹ Crore | ₹ / sq ft (saleable) | % of revenue (margin)
| Total revenue (A) | 803 | 8728.2609 | 100%
| Total cost (B) | 630.6053 | 6854.4057 | 78.53%
| EBITDA (A − B) | 172.3947 | 1873.8552 | 21.47%
| Tax | 44.8226 |  | 26% | Company
| PROFIT AFTER TAX (PAT) | 127.5721 | 1386.6529 | 15.89%
Tax is applied only on positive EBITDA (no tax credit is assumed on a loss).
| Developer's revenue share | 546.04
| Developer's cost (total cost excl. LO share) | 373.6453
| EBITDA margin on developer's share |  |  | 31.57%
D. JV REVENUE SPLIT (₹ Crore)
| Party | JV ratio % | Revenue share (₹ Cr) | Notes
| Developer | 68% | 546.04
| Landowner / JVP | 32% | 256.96
E. KEY INVESTMENT METRICS
| Metric | Value | Unit | Benchmark | Status | How it is calculated
| 1. Project IRR | 449.1% | % p.a. | 22% | ✅ Strong | Annualised IRR of quarterly project cash flows (before landowner share): (1 + quarterly IRR)^4 − 1
| 2. Developer IRR | 110.2% | % p.a. | 18% | ✅ Strong | Same, on developer cash flows (collections − costs − cash paid to landowner incl. advance timing)
| 3. Equity multiple (EM) | 1.4733 | x | 2 | ⚠️ Review | JV: developer's revenue share ÷ all costs excl. land, stamp duty & brokerage ¦ Outright: revenue ÷ total cost
| Initial investment used (₹ Cr) | 28.7094 |  |  |  | Section 7C (JV) / 7D (Outright) of INPUTS
| Project lifecycle (years) | 5
| 4. ROCE (annualised) | 120.1% | % p.a. | 30% | ✅ Strong | EBITDA ÷ initial investment ÷ project lifecycle
| Return on investment (₹ Cr) | 156.2815 |  |  |  | PAT + initial investment
| 5. CAGR | 40.34% | % p.a. | 30% | ✅ Strong | (Return on investment ÷ initial investment)^(1 ÷ lifecycle) − 1
| 6. PAT margin | 15.89% | % | 15% | ✅ Strong | PAT ÷ total revenue
| 7. EBITDA margin | 21.47% | % | 20% | ✅ Strong | EBITDA ÷ total revenue
| 8. Peak investment | 34.2873 | ₹ Cr | — |  | Largest cumulative funding need – reached in Q2 (Sep 2027)
| 9. Land cost to GDV | 32% | % | — |  | Land cost ÷ total revenue
| 10. Initial investment to GDV | 3.575% | % | — |  | Initial investment ÷ total revenue
| 11. Break-even quarter (project) | Q3 | Quarter | — |  | First quarter with positive net project cash flow (Dec 2027)
| 12. Break-even quarter (developer) | Q3 | Quarter | — |  | First quarter with positive net developer cash flow (Dec 2027)
| 13. Payback quarter (developer) | Q8 | Quarter | — |  | Cumulative developer cash returns to zero
| 14. Project NPV @ cost of equity | 251.6167 | ₹ Cr | — |  | Discounted at the cost of equity (Section 9 of INPUTS)
| 15. Developer NPV @ cost of equity | 90.6281 | ₹ Cr | —
| 16. Developer IRR (post-tax, indicative) | 83.89% | % p.a. | — |  | Tax spread in line with collections
| 17. Largest single-quarter deficit | 19.606 | ₹ Cr | — |  | 1244-style peak (one quarter)
| 18. Cash multiple (developer) | 4.3789 | x | — |  | Cash in ÷ cash out

## LISTS
LISTS & REFERENCE DATA (feeds dropdowns; edit with care)
Deal type | Taxable entity | Yes / No | Project type | Development zone | Product category | Curve – sales & construction | Curve – land payment | Curve – cost phasing | Cost basis (spare rows) | EDC basis | Contingency base | CLP trigger type | BAR authority | BAR land use | Compounding | CLP plan names (linked) | CLP plan status (linked) | Launch timing | Construction timing | Link event
JV | Company | Yes | Villa | Villa Development | Villa | Even | Upfront | Upfront | ₹/sq ft (total saleable area) | ₹/sq ft (total saleable area) | Construction cost | Booking + quarters | RIICO | Industrial | Annually | CLP – Villa | OK | Fixed quarter | Fixed quarter | Launch
Outright | LLP | No | Plotted | Apartment Development | Apartment | Front-loaded | Even | Even | % of total revenue | % of construction cost | All costs excl. land heads | Construction % complete | JDA | Residential | Half-yearly | CLP – Apartment | OK | Linked to another product | After own launch | Sales end
|  |  | Apartments | Plotted Development | Studio | Back-loaded | Front-loaded | Front-loaded | % of construction cost | Lump sum (₹ Cr) |  |  |  | Commercial | Quarterly | Plot – Development Linked | OK | After own construction start | Linked to another product | Construction start
|  |  | Mixed Development | Other / Clubhouse | Plot | S-curve | Back-loaded | Back-loaded | Lump sum (₹ Cr) | [5 empty] | Monthly | Down Payment Plan | OK |  |  | Construction 50%
[5 empty] | Commercial |  | S-curve | S-curve | ₹/sq yd (land area) | [6 empty] | CLP – 17-Floor Tower | OK |  |  | Construction end
[5 empty] | Institutional |  |  | Follow Construction | [8 empty] | Unused
[5 empty] | EWS/LIG |  |  | Follow Sales
Follow Collections
Follow Project Life
At Project End
LAND UNIT CONVERSION (units per 1 sq yd)
Unit | Per sq yd | Note
Sq ft | 9 | Exact (1 yd = 3 ft)
Sq metre | 0.83613 | Exact
Acre | 0.00020661 | 1 acre = 4,840 sq yd
Bigha | 0.00033058 | Rajasthan pucca bigha = 3,025 sq yd (varies by state – edit if needed)
Hectare | 8.3613e-05 | 1 ha = 10,000 sq m
Sq km | 8.3613e-07 | 1 sq km = 10,00,000 sq m
CURVE DEFINITIONS (used by the engine from Step 3)
Upfront | 100% in the start quarter.
Even | Same share every quarter (1/n).
Front-loaded | Weight of quarter i = n − i + 1, scaled to 100%.
Back-loaded | Weight of quarter i = i, scaled to 100%.
S-curve | Weight of quarter i = SIN(π × (i − 0.5) / n), scaled to 100% (slow–fast–slow).
Follow Construction | Same proportion as the products' construction progress.
Follow Sales | Same proportion as bookings.
Follow Collections | Same proportion as customer collections (e.g. JV landowner share).
Follow Project Life | Evenly from Q1 to the project's last active quarter.
At Project End | 100% in the project's last active quarter.